## Instructions
The Event Planning Template 4.0 has been developed by the PCC Education Advisory Sub-Committee to assist PCCs with their in-person or virtual events.
To help with your monthly or annual planning, there is a virtual and in-person worksheet for each month as well as a PCC Day virtual and in-person worksheet.
Each worksheet contains tasks that PCCs can consider completing to help ensure a successful event. The dates are based on planning an event at least 90-days in advance. As many PCCs have large events for PCC Day, the dates are based on planning 5-months in advance.
However, PCCs don’t always have 90-days or 120-days to plan an event. The worksheets will adjust to your timeline based on your actual dates that you begin planning. To adjust the worksheet:
In cell B3, enter the date of your event.
In cell B4, enter the first date of when you will start planning.
The Target Dates will now auto populate for each task.
You can add or delete tasks as needed.
In column D, enter each person’s name assigned to the task.
In column C, enter the date the task is completed.
To help with your budgeting, there is also three tabs - Expenses, Income, and Profit Loss Summary. All you need to do it plug in your actual values and the charts will automatically adjust.

## Event Checklist
Supplies for in-person event |  | Supplies for in-person event | Supplies for virtual event
| Projector & clicker (need batteries?) |  | Laptop or PC
| Laptop |  | Camera (optional)
| Power cords |  | Appropriate lighting
| Projection screen |  | Speakers and microphones (optional)
| Speakers, stands, microphones (need batteries?) |  | Virtual background (optional)
| Podium |  | PPT presentation
| PCC banner with stand |  | Script
| Sponsor slides |  | Water for speakers
| Ink pens |  | Hard copy printout of the presentation (optional)
| Office supplies - Tape, stapler, push pins, etc. |  | Pen and paper (to write notes if needed)
| Print name badges |  | Create slide with information (intermission slide)
| Print registration lists |  | Create slide with information (welcome page and placeholders)
| Event signage for location/parking |  | Sponsors Page
| Bios needed for introduction? |  | Activities (Music, Bingo, Spin the Wheel, Breakout Rooms, Polling)
| Water/sodas for speakers/attendees |  | Giveaways (Industry and Postal)
| Cooler and Ice |  | Survey (determine method)
Tablecloths/decorations
Printed handouts
Stamp art for speaker(s)?
Sponsor plaques at Holiday Luncheon
Reserved table placeholders
Cash box, receipt book & seed money
Masks
Sanitizer (registration table and each table)
Board activities during in-person event |  | Board activities during in-person event | Board activities during virutal event
| Pick up ice/water/sodas/food |  | Laptop or PC
| Place directional signage |  | Camera (optional)
| Welcome |  | Appropriate lighting
| Exit locations |  | Speakers and microphones (optional)
| Restroom locations |  | Virtual background (optional)
| Time of lunch (if part of the event) |  | Minutes
| Introduce guests/officials – or – |  | Agenda
| Go around room for self-introductions |  | Go around for self-introductions
| Recognize and thank sponsors |  | Recognize and thank sponsors
| Introduce speaker(s) |  | Introduce speakers
| Thank speaker – present gift? |  | Thank speaker - present gift?
Survey
Upcoming events
Closing
Thank you

## Expenses
Event Name |  |  | [Date]
Event Budget for Event Name: EXPENSES
Site | Estimated | Actual | Actual Cost Breakdown
Room and hall fees | 400 | 100
Site staff | 50 | 100
Equipment |  | 100
Tables and chairs
Total | 450 | 300
Decorations | Estimated | Actual
Flowers | 200 | 100
Candles | 500 | 200
Lighting
Balloons
Paper supplies
Total | 700 | 300
Publicity | Estimated | Actual
Graphics work | 500 | 800
Photocopying/Printing | 100
Postage
Total | 600 | 800
Miscellaneous | Estimated | Actual | Estimated vs. Actual
Telephone | 500 | 567
Transportation | 100
Stationery supplies
Fax services
Total | 600 | 567
Refreshments | Estimated | Actual
Food | 600 | 800
Drinks | 100
Linens
Staff and gratuities
Total | 700 | 800
Program | Estimated | Actual
Performers | 300 | 500
Speakers | 100
Travel
Hotel
Other
Total | 400 | 500
Prizes | Estimated | Actual
Ribbons/Plaques/Trophies | 200 | 300
Gifts | 100 | 50
Total | 300 | 350
Total Expenses | Estimated | Actual
| 3750 | 3617

## Income
Event Name
Event Budget for Event Name: INCOME
Admissions |  |  |  | Estimated | Actual | Income Comparison
Estimated | Actual
300 | 100 | Adults @ | 6 | 1800 | 600
200 | 50 | Children @ | 3 | 600 | 150
200 | 100 | Other @ | 1 | 200 | 100
|  |  |  | 2600 | 850
Ads in program |  |  |  | Estimated | Actual
Estimated | Actual
400 | 200 | Covers @ | 20 | 8000 | 4000
200 | 50 | Half-pages @ | 10 | 2000 | 500
100 | 50 | Quarter-pages @ | 10 | 1000 | 500
|  |  |  | 11000 | 5000
Exhibitors/vendors |  |  |  | Estimated | Actual
Estimated | Actual
150 | 100 | Large booths @ | 20 | 3000 | 2000
100 | 10 | Med. booths @ | 50 | 5000 | 500
50 | 2 | Small booths @ | 5 | 250 | 10
|  |  |  | 8250 | 2510
Sale of items |  |  |  | Estimated | Actual
Estimated | Actual
500 | 400 | Items @ | 20 | 10000 | 8000
300 | 200 | Items @ | 15 | 4500 | 3000
200 | 100 | Items @ | 10 | 2000 | 1000
100 | 0 | Items @ | 5 | 500 | 0
|  |  |  | 17000 | 12000
Total Income |  |  |  | Estimated | Actual
|  |  |  | 38850 | 20360

## Profit Loss Summary
Event Name |  |  |  | 2008-09-18
Event Budget for Event Name: PROFIT/LOSS SUMMARY
| Estimated | Actual | Profit vs. Loss
Total income | 38650 | 20310
Total Expenses | 3750 | 3617
Total profit (or loss)
| 34900 | 16693

## PCC Day In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-09-25
Today's date | 2022-07-21
Number of days to event | 66
Plan your event (location, length of event, # of topics) | 2022-07-21
Reserve Meeting Space (consider a place that does not need a deposit or will refund you if event is cancelled) | 2022-07-21
Set pricing for vendors, sponsors, attendees | 2022-07-21
Start soliciting vendors | 2022-07-21
Select additional topic (review Industry Speakers Bureau List) | 2022-07-21
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-07-21
Add to PCC Website, PCC Virtual Calendar, PCC Voice LinkedIn, and TeamSite (USPS) | 2022-07-21
Save the Date - mail and/or email | 2022-07-21
Formalize agenda and print for tables | 2022-07-27
Select caterer | 2022-07-27
Forecast costs - set attendance fee | 2022-08-11
Draft flyer/postcard | 2022-08-11
Set up registration page on Website | 2022-08-11
Finalize your PCC Paperwork with your PCC HQ Liaison | 2022-08-11
Mail flyer/postcard | 2022-08-21
Initial registration email | 2022-08-26
Determine if decorations for theme will be used and when to purchase them | 2022-08-26
Determine Thank You gift for speakers | 2022-08-26
Determine if prizes will be given out and the method (raffle drawing, contest) | 2022-08-26
Assign day of event responsibilities | 2022-08-26
Follow-up registration email | 2022-09-20
Verify count with caterer | 2022-09-20
Create "Day of Event" Task List | 2022-09-20
Create sign-in sheet | 2022-09-20
Create name tags | 2022-09-20
Thank you/survey email to attendees | 2022-09-30
Write-up for PCC Success Story | 2022-09-30
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-09-30
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-09-30

## PCC Day Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-09-22
Today's date | 2022-07-21
Number of days to event | 63
Determine date, time, format, partnering with other PCCs, dry run date and time | 2022-07-21
Select additional topic (review Industry Speakers Bureau List) | 2022-07-21
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-07-21
Add to PCC Website, PCC Virtual Calendar, PCC Voice LinkedIn, and TeamSite (USPS) | 2022-07-21
Save the Date - mail and/or email | 2022-07-21
Formalize agenda | 2022-07-24
Draft flyer/postcard | 2022-07-24
Set up registration page on Website | 2022-07-24
Mail flyer/postcard | 2022-08-18
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-08-18
Will you have Thank You gift for speakers | 2022-08-18
Initial registration email | 2022-08-18
Assign day of event responsibilities | 2022-08-18
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-08-18
Follow-up registration email | 2022-08-18
Create polling questions | 2022-08-18
Create breakout rooms | 2022-08-18
Create ice-breaker/activity | 2022-08-18
Thank you/survey email to attendees | 2022-09-27
Write-up for PCC Success Story | 2022-09-27
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-09-27
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-09-27

## Jan In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-01-15
Today's date | 2021-10-15
Number of days to event | 92
Select topic (review Industry Speakers Bureau List) | 2021-10-17
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2021-10-17
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2021-11-16
Save the Date - mail and/or email | 2021-11-16
Reserve Meeting Space | 2021-11-16
Select caterer | 2021-12-01
Formalize agenda and print for tables | 2021-12-01
Forecast costs - set attendance fee | 2021-12-01
Draft flyer/postcard | 2021-12-01
Set up registration page on Website | 2021-12-01
Mail flyer/postcard | 2021-12-11
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2021-12-16
Determine Thank You gift for speakers | 2021-12-16
Initial registration email | 2021-12-31
Assign day of event responsibilities | 2022-01-10
Follow-up registration email | 2022-01-10
Verify count with caterer | 2022-01-10
Create "Day of Event" Task List | 2022-01-10
Create sign-in sheet | 2022-01-10
Create name tags | 2022-01-10
Event (track # of attendees) | 2022-01-10
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-01-20
Thank you/survey email to attendees | 2022-01-20
Write-up for PCC Success Story | 2022-01-20
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-01-20
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-01-20

## Jan Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-01-15
Today's date | 2021-10-15
Number of days to event | 92
Select topic (review Industry Speakers Bureau List) | 2021-10-17
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2021-10-17
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2021-11-16
Save the Date - mail and/or email | 2021-11-16
Set up Zoom invite | 2021-11-16
Formalize agenda | 2021-12-01
Solicit for Sponsor (giveaway) | 2021-12-01
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2021-12-01
Forecast costs - set attendance fee | 2021-12-01
Draft flyer/postcard | 2021-12-01
Set up registration page on Website | 2021-12-11
Mail flyer/postcard | 2021-12-16
Determine Thank You gift for speaker(s) | 2021-12-16
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2021-12-16
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2021-12-16
Initial registration email | 2022-01-10
Assign day of event responsibilities | 2022-01-10
Follow-up registration email | 2022-01-14
Verify count | 2022-01-14
Create "Day of Event" Task List | 2022-01-14
Event (track # of attendees) | 2022-01-15
Thank you/survey email to attendees | 2022-01-25
Write-up for PCC Success Story | 2022-01-25
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-01-25
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-01-25
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-01-25

## Feb In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-02-17
Today's date | 2021-12-10
Number of days to event | 69
Select topic (review Industry Speakers Bureau List) | 2021-12-10
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2021-12-10
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2021-12-10
Save the Date - mail and/or email | 2021-12-10
Reserve Meeting Space | 2021-12-10
Select caterer | 2022-01-03
Formalize agenda and print for tables | 2022-01-03
Forecast costs - set attendance fee | 2022-01-03
Draft flyer/postcard | 2022-01-03
Set up registration page on Website | 2022-01-03
Mail flyer/postcard | 2022-01-13
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-01-18
Determine Thank You gift for speakers | 2022-01-18
Initial registration email | 2022-02-02
Assign day of event responsibilities | 2022-02-12
Follow-up registration email | 2022-02-12
Verify count with caterer | 2022-02-12
Create "Day of Event" Task List | 2022-02-12
Create sign-in sheet | 2022-02-12
Create name tags | 2022-02-12
Event (track # of attendees) | 2022-02-12
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-02-22
Thank you/survey email to attendees | 2022-02-22
Write-up for PCC Success Story | 2022-02-22
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-02-22
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-02-22

## Feb Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-02-26
Today's date | 2021-01-10
Number of days to event | 412
Select topic (review Industry Speakers Bureau List) | 2021-11-28
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2021-11-28
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2021-12-28
Save the Date - mail and/or email | 2021-12-28
Set up Zoom invite | 2021-12-28
Formalize agenda | 2022-01-12
Solicit for Sponsor (giveaway) | 2022-01-12
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-01-12
Forecast costs - set attendance fee | 2022-01-12
Draft flyer/postcard | 2022-01-12
Set up registration page on Website | 2022-01-22
Mail flyer/postcard | 2022-01-27
Determine Thank You gift for speaker(s) | 2022-01-27
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-01-27
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-01-27
Initial registration email | 2022-02-21
Assign day of event responsibilities | 2022-02-21
Follow-up registration email | 2022-02-25
Verify count | 2022-02-25
Create "Day of Event" Task List | 2022-02-25
Event (track # of attendees) | 2022-02-26
Thank you/survey email to attendees | 2022-03-08
Write-up for PCC Success Story | 2022-03-08
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-03-08
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-03-08
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-03-08

## Mar In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-03-30
Today's date | 2021-12-17
Number of days to event | 103
Select topic (review Industry Speakers Bureau List) | 2021-12-30
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2021-12-30
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-01-29
Save the Date - mail and/or email | 2022-01-29
Reserve Meeting Space | 2022-01-29
Select caterer | 2022-02-13
Formalize agenda and print for tables | 2022-02-13
Forecast costs - set attendance fee | 2022-02-13
Draft flyer/postcard | 2022-02-13
Set up registration page on Website | 2022-02-13
Mail flyer/postcard | 2022-02-23
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-02-28
Determine Thank You gift for speakers | 2022-02-28
Initial registration email | 2022-03-15
Assign day of event responsibilities | 2022-03-25
Follow-up registration email | 2022-03-25
Verify count with caterer | 2022-03-25
Create "Day of Event" Task List | 2022-03-25
Create sign-in sheet | 2022-03-25
Create name tags | 2022-03-25
Event (track # of attendees) | 2022-03-25
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-04-04
Thank you/survey email to attendees | 2022-04-04
Write-up for PCC Success Story | 2022-04-04
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-04-04
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-04-04

## Mar Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-03-19
Today's date | 2021-01-15
Number of days to event | 428
Select topic (review Industry Speakers Bureau List) | 2021-12-19
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2021-12-19
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-01-18
Save the Date - mail and/or email | 2022-01-18
Set up Zoom invite | 2022-01-18
Formalize agenda | 2022-02-02
Solicit for Sponsor (giveaway) | 2022-02-02
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-02-02
Forecast costs - set attendance fee | 2022-02-02
Draft flyer/postcard | 2022-02-02
Set up registration page on Website | 2022-02-12
Mail flyer/postcard | 2022-02-17
Determine Thank You gift for speaker(s) | 2022-02-17
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-02-17
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-02-17
Initial registration email | 2022-03-14
Assign day of event responsibilities | 2022-03-14
Follow-up registration email | 2022-03-18
Verify count | 2022-03-18
Create "Day of Event" Task List | 2022-03-18
Event (track # of attendees) | 2022-03-19
Thank you/survey email to attendees | 2022-03-29
Write-up for PCC Success Story | 2022-03-29
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-03-29
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-03-29
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-03-29

## Apr In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-04-01
Today's date | 2021-01-18
Number of days to event | 438
Select topic (review Industry Speakers Bureau List) | 2022-01-01
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-01-01
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-01-31
Save the Date - mail and/or email | 2022-01-31
Reserve Meeting Space | 2022-01-31
Select caterer | 2022-02-15
Formalize agenda and print for tables | 2022-02-15
Forecast costs - set attendance fee | 2022-02-15
Draft flyer/postcard | 2022-02-15
Set up registration page on Website | 2022-02-15
Mail flyer/postcard | 2022-02-25
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-03-02
Determine Thank You gift for speakers | 2022-03-02
Initial registration email | 2022-03-17
Assign day of event responsibilities | 2022-03-27
Follow-up registration email | 2022-03-27
Verify count with caterer | 2022-03-27
Create "Day of Event" Task List | 2022-03-27
Create sign-in sheet | 2022-03-27
Create name tags | 2022-03-27
Event (track # of attendees) | 2022-03-27
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-04-06
Thank you/survey email to attendees | 2022-04-06
Write-up for PCC Success Story | 2022-04-06
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-04-06
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-04-06

## April Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-04-20
Today's date | 2021-03-22
Number of days to event | 394
Select topic (review Industry Speakers Bureau List) | 2022-01-20
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-01-20
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-02-19
Save the Date - mail and/or email | 2022-02-19
Set up Zoom invite | 2022-02-19
Formalize agenda | 2022-03-06
Solicit for Sponsor (giveaway) | 2022-03-06
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-03-06
Forecast costs - set attendance fee | 2022-03-06
Draft flyer/postcard | 2022-03-06
Set up registration page on Website | 2022-03-16
Mail flyer/postcard | 2022-03-21
Determine Thank You gift for speaker(s) | 2022-03-21
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-03-21
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-03-21
Initial registration email | 2022-04-15
Assign day of event responsibilities | 2022-04-15
Follow-up registration email | 2022-04-19
Verify count | 2022-04-19
Create "Day of Event" Task List | 2022-04-19
Event (track # of attendees) | 2022-04-20
Thank you/survey email to attendees | 2022-04-30
Write-up for PCC Success Story | 2022-04-30
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-04-30
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-04-30
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-04-30

## May In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-05-07
Today's date | 2021-03-31
Number of days to event | 402
Select topic (review Industry Speakers Bureau List) | 2022-02-06
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-02-06
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-03-08
Save the Date - mail and/or email | 2022-03-08
Reserve Meeting Space | 2022-03-08
Select caterer | 2022-03-23
Formalize agenda and print for tables | 2022-03-23
Forecast costs - set attendance fee | 2022-03-23
Draft flyer/postcard | 2022-03-23
Set up registration page on Website | 2022-03-23
Mail flyer/postcard | 2022-04-02
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-04-07
Determine Thank You gift for speakers | 2022-04-07
Initial registration email | 2022-04-22
Assign day of event responsibilities | 2022-05-02
Follow-up registration email | 2022-05-02
Verify count with caterer | 2022-05-02
Create "Day of Event" Task List | 2022-05-02
Create sign-in sheet | 2022-05-02
Create name tags | 2022-05-02
Event (track # of attendees) | 2022-05-02
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-05-12
Thank you/survey email to attendees | 2022-05-12
Write-up for PCC Success Story | 2022-05-12
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-05-12
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-05-12

## May Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-05-18
Today's date | 2021-03-10
Number of days to event | 434
Select topic (review Industry Speakers Bureau List) | 2022-02-17
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-02-17
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-03-19
Save the Date - mail and/or email | 2022-03-19
Set up Zoom invite | 2022-03-19
Formalize agenda | 2022-04-03
Solicit for Sponsor (giveaway) | 2022-04-03
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-04-03
Forecast costs - set attendance fee | 2022-04-03
Draft flyer/postcard | 2022-04-03
Set up registration page on Website | 2022-04-13
Mail flyer/postcard | 2022-04-18
Determine Thank You gift for speaker(s) | 2022-04-18
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-04-18
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-04-18
Initial registration email | 2022-05-13
Assign day of event responsibilities | 2022-05-13
Follow-up registration email | 2022-05-17
Verify count | 2022-05-17
Create "Day of Event" Task List | 2022-05-17
Event (track # of attendees) | 2022-05-18
Thank you/survey email to attendees | 2022-05-28
Write-up for PCC Success Story | 2022-05-28
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-05-28
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-05-28
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-05-28

## June In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-06-09
Today's date | 2021-04-02
Number of days to event | 433
Select topic (review Industry Speakers Bureau List) | 2022-03-11
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-03-11
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-04-10
Save the Date - mail and/or email | 2022-04-10
Reserve Meeting Space | 2022-04-10
Select caterer | 2022-04-25
Formalize agenda and print for tables | 2022-04-25
Forecast costs - set attendance fee | 2022-04-25
Draft flyer/postcard | 2022-04-25
Set up registration page on Website | 2022-04-25
Mail flyer/postcard | 2022-05-05
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-05-10
Determine Thank You gift for speakers | 2022-05-10
Initial registration email | 2022-05-25
Assign day of event responsibilities | 2022-06-04
Follow-up registration email | 2022-06-04
Verify count with caterer | 2022-06-04
Create "Day of Event" Task List | 2022-06-04
Create sign-in sheet | 2022-06-04
Create name tags | 2022-06-04
Event (track # of attendees) | 2022-06-04
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-06-14
Thank you/survey email to attendees | 2022-06-14
Write-up for PCC Success Story | 2022-06-14
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-06-14
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-06-14

## June Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-06-22
Today's date | 2021-04-02
Number of days to event | 446
Select topic (review Industry Speakers Bureau List) | 2022-03-24
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-03-24
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-04-23
Save the Date - mail and/or email | 2022-04-23
Set up Zoom invite | 2022-04-23
Formalize agenda | 2022-05-08
Solicit for Sponsor (giveaway) | 2022-05-08
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-05-08
Forecast costs - set attendance fee | 2022-05-08
Draft flyer/postcard | 2022-05-08
Set up registration page on Website | 2022-05-18
Mail flyer/postcard | 2022-05-23
Determine Thank You gift for speaker(s) | 2022-05-23
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-05-23
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-05-23
Initial registration email | 2022-06-17
Assign day of event responsibilities | 2022-06-17
Follow-up registration email | 2022-06-21
Verify count | 2022-06-21
Create "Day of Event" Task List | 2022-06-21
Event (track # of attendees) | 2022-06-22
Thank you/survey email to attendees | 2022-07-02
Write-up for PCC Success Story | 2022-07-02
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-07-02
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-07-02
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-07-02

## July In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-07-19
Today's date | 2021-05-27
Number of days to event | 418
Select topic (review Industry Speakers Bureau List) | 2022-04-20
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-04-20
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-05-20
Save the Date - mail and/or email | 2022-05-20
Reserve Meeting Space | 2022-05-20
Select caterer | 2022-06-04
Formalize agenda and print for tables | 2022-06-04
Forecast costs - set attendance fee | 2022-06-04
Draft flyer/postcard | 2022-06-04
Set up registration page on Website | 2022-06-04
Mail flyer/postcard | 2022-06-14
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-06-19
Determine Thank You gift for speakers | 2022-06-19
Initial registration email | 2022-07-04
Assign day of event responsibilities | 2022-07-14
Follow-up registration email | 2022-07-14
Verify count with caterer | 2022-07-14
Create "Day of Event" Task List | 2022-07-14
Create sign-in sheet | 2022-07-14
Create name tags | 2022-07-14
Event (track # of attendees) | 2022-07-14
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-07-24
Thank you/survey email to attendees | 2022-07-24
Write-up for PCC Success Story | 2022-07-24
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-07-24
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-07-24

## July Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-07-01
Today's date | 2021-06-09
Number of days to event | 387
Select topic (review Industry Speakers Bureau List) | 2022-04-02
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-04-02
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-05-02
Save the Date - mail and/or email | 2022-05-02
Set up Zoom invite | 2022-05-02
Formalize agenda | 2022-05-17
Solicit for Sponsor (giveaway) | 2022-05-17
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-05-17
Forecast costs - set attendance fee | 2022-05-17
Draft flyer/postcard | 2022-05-17
Set up registration page on Website | 2022-05-27
Mail flyer/postcard | 2022-06-01
Determine Thank You gift for speaker(s) | 2022-06-01
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-06-01
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-06-01
Initial registration email | 2022-06-26
Assign day of event responsibilities | 2022-06-26
Follow-up registration email | 2022-06-30
Verify count | 2022-06-30
Create "Day of Event" Task List | 2022-06-30
Event (track # of attendees) | 2022-07-01
Thank you/survey email to attendees | 2022-07-11
Write-up for PCC Success Story | 2022-07-11
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-07-11
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-07-11
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-07-11

## Aug In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-08-16
Today's date | 2021-05-10
Number of days to event | 463
Select topic (review Industry Speakers Bureau List) | 2022-05-18
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-05-18
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-06-17
Save the Date - mail and/or email | 2022-06-17
Reserve Meeting Space | 2022-06-17
Select caterer | 2022-07-02
Formalize agenda and print for tables | 2022-07-02
Forecast costs - set attendance fee | 2022-07-02
Draft flyer/postcard | 2022-07-02
Set up registration page on Website | 2022-07-02
Mail flyer/postcard | 2022-07-12
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-07-17
Determine Thank You gift for speakers | 2022-07-17
Initial registration email | 2022-08-01
Assign day of event responsibilities | 2022-08-11
Follow-up registration email | 2022-08-11
Verify count with caterer | 2022-08-11
Create "Day of Event" Task List | 2022-08-11
Create sign-in sheet | 2022-08-11
Create name tags | 2022-08-11
Event (track # of attendees) | 2022-08-11
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-08-21
Thank you/survey email to attendees | 2022-08-21
Write-up for PCC Success Story | 2022-08-21
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-08-21
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-08-21

## Aug Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-08-25
Today's date | 2021-07-07
Number of days to event | 414
Select topic (review Industry Speakers Bureau List) | 2022-05-27
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-05-27
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-06-26
Save the Date - mail and/or email | 2022-06-26
Set up Zoom invite | 2022-06-26
Formalize agenda | 2022-07-11
Solicit for Sponsor (giveaway) | 2022-07-11
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-07-11
Forecast costs - set attendance fee | 2022-07-11
Draft flyer/postcard | 2022-07-11
Set up registration page on Website | 2022-07-21
Mail flyer/postcard | 2022-07-26
Determine Thank You gift for speaker(s) | 2022-07-26
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-07-26
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-07-26
Initial registration email | 2022-08-20
Assign day of event responsibilities | 2022-08-20
Follow-up registration email | 2022-08-24
Verify count | 2022-08-24
Create "Day of Event" Task List | 2022-08-24
Event (track # of attendees) | 2022-08-25
Thank you/survey email to attendees | 2022-09-04
Write-up for PCC Success Story | 2022-09-04
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-09-04
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-09-04
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-09-04

## Sep In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-09-01
Today's date | 2021-08-02
Number of days to event | 395
Select topic (review Industry Speakers Bureau List) | 2022-06-03
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-06-03
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-07-03
Save the Date - mail and/or email | 2022-07-03
Reserve Meeting Space | 2022-07-03
Select caterer | 2022-07-18
Formalize agenda and print for tables | 2022-07-18
Forecast costs - set attendance fee | 2022-07-18
Draft flyer/postcard | 2022-07-18
Set up registration page on Website | 2022-07-18
Mail flyer/postcard | 2022-07-28
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-08-02
Determine Thank You gift for speakers | 2022-08-02
Initial registration email | 2022-08-17
Assign day of event responsibilities | 2022-08-27
Follow-up registration email | 2022-08-27
Verify count with caterer | 2022-08-27
Create "Day of Event" Task List | 2022-08-27
Create sign-in sheet | 2022-08-27
Create name tags | 2022-08-27
Event (track # of attendees) | 2022-08-27
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-09-06
Thank you/survey email to attendees | 2022-09-06
Write-up for PCC Success Story | 2022-09-06
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-09-06
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-09-06

## Sep Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-09-02
Today's date | 2021-07-13
Number of days to event | 416
Select topic (review Industry Speakers Bureau List) | 2022-06-04
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-06-04
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-07-04
Save the Date - mail and/or email | 2022-07-04
Set up Zoom invite | 2022-07-04
Formalize agenda | 2022-07-19
Solicit for Sponsor (giveaway) | 2022-07-19
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-07-19
Forecast costs - set attendance fee | 2022-07-19
Draft flyer/postcard | 2022-07-19
Set up registration page on Website | 2022-07-29
Mail flyer/postcard | 2022-08-03
Determine Thank You gift for speaker(s) | 2022-08-03
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-08-03
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-08-03
Initial registration email | 2022-08-28
Assign day of event responsibilities | 2022-08-28
Follow-up registration email | 2022-09-01
Verify count | 2022-09-01
Create "Day of Event" Task List | 2022-09-01
Event (track # of attendees) | 2022-09-02
Thank you/survey email to attendees | 2022-09-12
Write-up for PCC Success Story | 2022-09-12
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-09-12
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-09-12
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-09-12

## Oct In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-10-19
Today's date | 2021-08-19
Number of days to event | 426
Select topic (review Industry Speakers Bureau List) | 2022-07-21
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-07-21
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-08-20
Save the Date - mail and/or email | 2022-08-20
Reserve Meeting Space | 2022-08-20
Select caterer | 2022-09-04
Formalize agenda and print for tables | 2022-09-04
Forecast costs - set attendance fee | 2022-09-04
Draft flyer/postcard | 2022-09-04
Set up registration page on Website | 2022-09-04
Mail flyer/postcard | 2022-09-14
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-09-19
Determine Thank You gift for speakers | 2022-09-19
Initial registration email | 2022-10-04
Assign day of event responsibilities | 2022-10-14
Follow-up registration email | 2022-10-14
Verify count with caterer | 2022-10-14
Create "Day of Event" Task List | 2022-10-14
Create sign-in sheet | 2022-10-14
Create name tags | 2022-10-14
Event (track # of attendees) | 2022-10-14
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-10-24
Thank you/survey email to attendees | 2022-10-24
Write-up for PCC Success Story | 2022-10-24
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-10-24
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-10-24

## Oct Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-10-14
Today's date | 2021-09-10
Number of days to event | 399
Select topic (review Industry Speakers Bureau List) | 2022-07-16
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-07-16
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-08-15
Save the Date - mail and/or email | 2022-08-15
Set up Zoom invite | 2022-08-15
Formalize agenda | 2022-08-30
Solicit for Sponsor (giveaway) | 2022-08-30
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-08-30
Forecast costs - set attendance fee | 2022-08-30
Draft flyer/postcard | 2022-08-30
Set up registration page on Website | 2022-09-09
Mail flyer/postcard | 2022-09-14
Determine Thank You gift for speaker(s) | 2022-09-14
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-09-14
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-09-14
Initial registration email | 2022-10-09
Assign day of event responsibilities | 2022-10-09
Follow-up registration email | 2022-10-13
Verify count | 2022-10-13
Create "Day of Event" Task List | 2022-10-13
Event (track # of attendees) | 2022-10-14
Thank you/survey email to attendees | 2022-10-24
Write-up for PCC Success Story | 2022-10-24
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-10-24
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-10-24
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-10-24

## Nov In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-11-02
Today's date | 2021-07-19
Number of days to event | 471
Select topic (review Industry Speakers Bureau List) | 2022-08-04
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-08-04
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-09-03
Save the Date - mail and/or email | 2022-09-03
Reserve Meeting Space | 2022-09-03
Select caterer | 2022-09-18
Formalize agenda and print for tables | 2022-09-18
Forecast costs - set attendance fee | 2022-09-18
Draft flyer/postcard | 2022-09-18
Set up registration page on Website | 2022-09-18
Mail flyer/postcard | 2022-09-28
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-10-03
Determine Thank You gift for speakers | 2022-10-03
Initial registration email | 2022-10-18
Assign day of event responsibilities | 2022-10-28
Follow-up registration email | 2022-10-28
Verify count with caterer | 2022-10-28
Create "Day of Event" Task List | 2022-10-28
Create sign-in sheet | 2022-10-28
Create name tags | 2022-10-28
Event (track # of attendees) | 2022-10-28
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-11-07
Thank you/survey email to attendees | 2022-11-07
Write-up for PCC Success Story | 2022-11-07
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-11-07
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-11-07

## Nov Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-11-01
Today's date | 2021-09-16
Number of days to event | 411
Select topic (review Industry Speakers Bureau List) | 2022-08-03
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-08-03
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-09-02
Save the Date - mail and/or email | 2022-09-02
Set up Zoom invite | 2022-09-02
Formalize agenda | 2022-09-17
Solicit for Sponsor (giveaway) | 2022-09-17
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-09-17
Forecast costs - set attendance fee | 2022-09-17
Draft flyer/postcard | 2022-09-17
Set up registration page on Website | 2022-09-27
Mail flyer/postcard | 2022-10-02
Determine Thank You gift for speaker(s) | 2022-10-02
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-10-02
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-10-02
Initial registration email | 2022-10-27
Assign day of event responsibilities | 2022-10-27
Follow-up registration email | 2022-10-31
Verify count | 2022-10-31
Create "Day of Event" Task List | 2022-10-31
Event (track # of attendees) | 2022-11-01
Thank you/survey email to attendees | 2022-11-11
Write-up for PCC Success Story | 2022-11-11
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-11-11
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-11-11
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-11-11

## Dec In-Person Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-12-10
Today's date | 2021-08-12
Number of days to event | 485
Select topic (review Industry Speakers Bureau List) | 2022-09-11
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-09-11
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-10-11
Save the Date - mail and/or email | 2022-10-11
Reserve Meeting Space | 2022-10-11
Select caterer | 2022-10-26
Formalize agenda and print for tables | 2022-10-26
Forecast costs - set attendance fee | 2022-10-26
Draft flyer/postcard | 2022-10-26
Set up registration page on Website | 2022-10-26
Mail flyer/postcard | 2022-11-05
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-11-10
Determine Thank You gift for speakers | 2022-11-10
Initial registration email | 2022-11-25
Assign day of event responsibilities | 2022-12-05
Follow-up registration email | 2022-12-05
Verify count with caterer | 2022-12-05
Create "Day of Event" Task List | 2022-12-05
Create sign-in sheet | 2022-12-05
Create name tags | 2022-12-05
Event (track # of attendees) | 2022-12-05
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-12-15
Thank you/survey email to attendees | 2022-12-15
Write-up for PCC Success Story | 2022-12-15
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-12-15
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-12-15

## Dec Virtual Event
| Target Date | Actual Date | Person Assigned
Date of event | 2022-12-01
Today's date | 2021-11-13
Number of days to event | 383
Select topic (review Industry Speakers Bureau List) | 2022-09-02
Select speaker (Use Industry Speakers Bureau List or fill out HQ Request Form) | 2022-09-02
Add to PCC Website, PCC Virutal Calendar, PCC Voice LinkedIn posting, and TeamSite (USPS) | 2022-10-02
Save the Date - mail and/or email | 2022-10-02
Set up Zoom invite | 2022-10-02
Formalize agenda | 2022-10-17
Solicit for Sponsor (giveaway) | 2022-10-17
Determine activities (welcome or sponsor slide, polling, survey, breakout rooms, spin the wheel) | 2022-10-17
Forecast costs - set attendance fee | 2022-10-17
Draft flyer/postcard | 2022-10-17
Set up registration page on Website | 2022-10-27
Mail flyer/postcard | 2022-11-01
Determine Thank You gift for speaker(s) | 2022-11-01
Determine if prizes will be given out and the method (raffle drawing, contest, spin the wheel) | 2022-11-01
Determine if a Dry Run will be needed. If yes, set up date and send out Zoom invite. | 2022-11-01
Initial registration email | 2022-11-26
Assign day of event responsibilities | 2022-11-26
Follow-up registration email | 2022-11-30
Verify count | 2022-11-30
Create "Day of Event" Task List | 2022-11-30
Event (track # of attendees) | 2022-12-01
Thank you/survey email to attendees | 2022-12-11
Write-up for PCC Success Story | 2022-12-11
Track Members for Certificate and Track Program - add to your spreadsheet and mail out appropriate certificate if applicable | 2022-12-11
Write-up a comment for Speakers Bureau List if Industry Speaker was used | 2022-12-11
"Lessons Learned" session, add information in PCC Binder, Write-Up for PCC Leadership Award | 2022-12-11