## Issues List
Issue # | Type | Date Raised | Item | Raised By | Category | Release | Owner | Resolution | Status | Recommendation
7 | Question | 2015-10-07 | Will any additional AQS services be brought in-scope by the project? Specifically NCOA license fees. |  | ACS | Release 3 | Jennifer Howard | NCSC is reviewing AQS and proposing a timeline and prioritization. As soon as dates ae available they will be communicated | In Progress | Review with WG on 3/21
20 | Question | 2015-11-19 | Review needed around security - how do you prevent a BSA that leaves a company from sharing the password? | John W | General | Release 1 | Barbara/Ludmila | The USPS can't prevent Users from Sharing their passwords. They can recommend that BSA's leaving the company transfer their priveleges | Resolved | FAQ and walkthru - changes pending with WG 183
21 | Question | 2015-11-19 | Security issues: Q1: What if the BSA leaves and still has access; and no one else has access? Q2: Is there a disaster recovery plan for individuals in orgs with key access to critical information? Q3: How does the USPS know it is ok to reassign access? Q4: How can unauthorized access to someone's ACH account be prevented? - Notification/Disable process? -Needs to be a validation process to confirm identity before reassigning a BSA role based on a phone call | Michelle | General | Release 1 | Barbara/Ludmila | In referene to Q1 & 3; If the BSA leaves the company or leaves their role with the company, the USPS will accept an email to change the BSA. Q2; No one could clarify question so it is not being addressed by WG173. Q4; The USPS does not have direct access to customer banking information and would need to be notified by the customer or bank if this type of issue existed. After being contacted by the customer, the USPS could suspend the account. | Resolved
35 | Question | 2016-01-14 | Can price change data be incorporated into the historical view so users could see budget impact after a price change by selecting a future date range? |  | General | N/A | Jennifer Howard | Need to confirm as a requirement with IV-Payment proposal. IV to provide all the fields, mailers will have to incorporate their own price change information. | Resolved | IV
39 | Suggestion | 2016-01-27 | Enterprise Payment - mailers request the ability to create a scheduled report (push report vs. a pull report) | Angelo | Reports | Release 2 | Jennifer Howard | Planned EPS scope through IV-Payment will allow a customer to setup a scheduled recurring report that would run at a specified time each day/week/month and be saved to the "Scheduled Reports". | Resolved | IV-Payment Walkthrough Wireframes 4/11/18
2 | Issue | 2015-10-07 | There are limitations especially with Mail Anywhere with not having the ability to link a permit to more than one CRID. |  | CRIDs | Release 2 | Josefina Cabatu | Review requirements for IV-Payment; make recommendations for filtered reports to accommodate this scenario. Issue will be tracked through EPS Known Issues list with UG11. Permits can only be linked to 1 CRID | Resolved | Permits can only be linked to 1 CRID
16 | ? | 2015-10-21 | Automated balance check like with mail.xml |  | Permits |  | Jennifer Howard | Change Request to be submitted to EPS. Issue will be tracked through EPS Known Issues list with UG11. | Resolved | Move to UG11
31 | Question | 2016-01-06 | Can online payment be used instead of a check to purchase stamps? | Angelo | Checks | Release 3 | Ingrid Molinary | In Release 4 (Aug 2018), customers will be able to buy Bulk Stamps/StampsNow with their Enterprise Payment account. Currently customers can buy stamps on USPS.com with a credit card. We will look into the possibility of using an Enterprise Payment account to pay for stamps on USPS.com. | Resolved | Tentatively planned for August, a concept shuld be available to be shared prior to WG173 sunset
13 | Suggestion | 2015-10-21 | Need customer friendly capability to link permits, today it does not work well and a lot of times requires contacting help desk (failed validation) | Linda | Permits | Release 2 | Josefina Cabatu | Confirm current approach after feedback from WG 184 and if still needed, work with UG11 to further resolve. EPS provided users with an easier ability to link permits via a dropdown. | Resolved
25 | Question | 2015-11-19 | Will EPS handle Pending Periodicals that require setting up a permit and depositing a check prior to authorization? | Jack Wagner | EPS | Release 2 | Josefina Cabatu | Review EPS integration with WG 173 on 3/21. EPS does all Periodicals and Pending Periodicals. | Resolved | walkthru 5/2/18
49 | Issue | 2016-04-06 | Multiple mailers reported issues with Full-Service waiver eligibility and the auto-renewal process for permit fees in CAPS. The Full-Service waiver is not always occurring when the 90% threshold is met and maintained. USPS requests that mailers experiencing this issue open a Help Desk ticket so instances can be resolved. This process will be impacted with the implementation of Payment Modernization, and USPS will share the proposed approach with this group as user stories are finalized. |  | Permit fees | Release 2 | Josefina Cabatu | Full Service Fee waivers will be handled the same as non-EPS. It is based on FS Percentage. If you fall below the required % then on the next business day, you would be charged the permit fees Auto-fee renewal used to be taken automatically without looking at FS % but that has now changed. | Resolved | walkthru
32 | Issue | 2016-01-14 | Presort mailers will be impacted by Enterprise Payment because mailers are being driven to online payment. Presort mailers currently meter mail and most have an arrangement with their customers to split the savings. If their customers are being driven to online payment instead though this would have an indirect impact on the presort industry. | not captured | General | N/A | Jennifer Howard | Need further clarification from the person who brought this up | Resolved
40 | Question | 2016-01-27 | PostalOne! - confirm current archiving rules (is it 13 months or 14 months) | Randy | Archiving | Release 2 | Josefina Cabatu | PostalOne! archives for 14 months. CAPS archives for 12 months. EPS archives for 24 months. | Resolved
9 | Suggestion | 2015-10-21 | Customers need to be able to key off of Order Reference ID and Customer Reference ID etc. - would like to have data in the same format as CAPS today | Todd | CAPS | Release 2 | Jennifer Howard | EPS accepts this information when passed through PostalOne! and displays on Mailing Details report. | Resolved
3 | Question | 2015-10-07 | What steps will be required of customers to migrate PO Boxes from locally managed to the new Payment Modernization platform. |  | PO Boxes | Release 1 | Ingrid Molinary | A document with steps on how to migrate will be provided to PO Box/Caller/Reserve customers | Resolved
4 | Question | 2015-10-07 | Should customers not currently utilizing POBOL migrate to POBOL now or wait until the new Payment Modernization platform goes live? |  | PO Boxes | Release 1 | Ingrid Molinary | Business customers should should wait until Enterprise Payment and ePOBOL go live before migrating (POBOL is for residential customers). Communications will be sent after the pilot inviting existing po box/caller/reserve customers to migrate to ePOBOL and EPS. Communications and instructions will be provided. | Resolved
5 | Question | 2015-10-07 | Will initial fees be for establishing a PO Box be payable online with the new Payment Modernization platform? |  | PO Boxes | Release 1 | Ingrid Molinary | Yes, all PO Box/Caller/Reserve fees must be paid online using Enterprise Payment after the customer has migrated their boxes to the online platform. | Resolved
6 | Question | 2015-10-07 | Regarding the Payment Modernization platform and PO Boxes - is it possible to manage some boxes online centrally while others are managed locally? Can only some of a customer’s PO Boxes be migrated to the Payment Modernization platform. |  | PO Boxes | Release 1 | Ingrid Molinary | Yes, the customer can choose which boxes to migrate and manage online and which to manage locally | Resolved
27 | Action | 2015-12-02 | Prior to Jan MTAC meeting need to identify all use cases regarding payment transactions Identified use cases: 1: Mail owner pays postage via CAPS 2: Mail owner submits check payable to Postmaster to MSP for deposit into Mail Owners permit (non-CAPS) 3:Mail owner submits check payable to Postmaster to MSP for deposit into MSP's Permit (non-CAPS) 4: Stamps are purchased using a check 5: Postal Refunds |  | Checks | Release 2 | Jennifer Howard | Reviewed with user roles at face-to-face 3/1. | Resolved
1 | Question | 2015-10-07 | Will consideration be given to link permit to more than one CRID? This becomes a particular concern when mailing pieces participating in an incentive program, as there is a constrain of linking 1 permit to 1 CRID | Linda/Susan | CRIDs | Release 2 | Josefina Cabatu | Permits are linked to a single EPA, although the permit and EPA may be managed from separate CRIDs. Reviewed with user roles at face-to-face 3/1. | Resolved | review with user roles at face-to-face
10 | Question | 2015-10-21 | What physically will happen if there is an ACH debit bounce back? Will the mail still go through? How will customer be alerted? |  | Payment | Release 1 | Jennifer Howard | The mail will still go through and the customer will be alerted about the ACH Debit return via email notification. | Resolved | update FAQs and walkthru with group
11 | Suggestion | 2015-10-21 | Industry leads compile feedback from industry about CRID clean-up and what value there would be to CRID clean-up | Todd | CRIDs | N/A | Jennifer/Barbara | 11/10 Linda provided examples of CRID Clean up needed: ex - User created CRIDs inadvertently by typing in an address that already existed; Plant closures. Falls under WG 184. | Resolved | WG 184
12 | Suggestion | 2015-10-21 | CRID management Need to improve this in general | Linda | CRIDs | N/A | Jennifer/Barbara | Falls under WG 184 and WG 183. | Resolved | WG 184
14 | Suggestion | 2015-10-21 | Ensure that action items are brought from older meetings | Linda | General | N/A | Jennifer Howard | Jennifer will ensure | Resolved
15 | Action | 2015-10-21 | Pilot volunteers need to be identified |  | PO Boxes | Release 1 | Ingrid Molinary | 6 pilot customers for PO Boxes/Callers/Reserves has been identified | Resolved
17 | Action | 2015-11-10 | WG needs to provide feedback on use cases regarding check payments |  | Checks |  | Jennifer Howard |  | Resolved
18 | Question | 2015-11-10 | How will the multi-factor authentication work? | Todd Black | General | N/A | Jennifer Howard | Multi factor authentication is not currently in scope, but will be considered for a future release. | Resolved
19 | Question | 2015-11-19 | How is payment for opening a box handled? Service Fee? Renewal Fees |  | PO Boxes | Release 1 | Ingrid Molinary | Customers that open a new box on ePOBOL will be charged the 12 month fee. 12 months later, the customer will be charged a renewal fee for their box. | Resolved
22 | Action | 2015-11-19 | WG to identify relationships, user roles, and scenarios to consider in setting up ability to conduct transactions; think about how they will use this information and be prepared to determine who will need access? - who besides the Mail Owner might want access and what would you want them to have access to? |  | User Roles | Release 1 | Ashley White | Scenarios from WG were reviewed and EPS user roles were determined accordingly | Resolved
23 | Action | 2015-11-19 | Sub-group needs to be formed to map out use cases - payment account access, user roles, relationships etc. |  | User Roles | Release 1 | Jennifer Howard | Sub-Group established | Resolved
24 | Action | 2015-11-19 | WG needs a representative from banking industry |  | General | N/A | Jennifer Howard | Resolved. The workgroup now has representatives from the banking industry. | Resolved
26 | Action | 2015-12-02 | Sub-group participants to expand on 4 use cases identified in 11/19 meeting and being to flow charting |  | General | N/A | Jennifer Howard | Action item | Resolved
28 | Question | 2015-12-16 | What is the critical data that is necessary to provide customer to manage and pay for all their PO Boxes - what would be pertinent for a dashboard v. a reporting view? |  | PO Boxes | Release 1 | Ingrid Molinary | The ePOBOL report data has been outlined for Relase 1. After the pilot additional suggestions can be made to enhance the reports. | Resolved
29 | Action | 2015-12-16 | There is a need to identify and take into account the scenarios with MSPs |  | General | N/A | Jennifer Howard | This was part of the user role use case discussion #22 | Resolved
30 | Enhancement | 2016-01-06 | Can Enterprise Payment include technology to accept photo or electronic entry of checks so mailers don't have to drive to a post office to deposit | Angelo | Checks | N/A | Jennifer Howard | This solution is being worked and may be included in a later release | Resolved
33 | Question | 2016-01-14 | Will assessments be captured separately from transactions in the dashboard and will there be a reason code or other differentiator to clearly identify assessments? (coordinate solution with UG10) | David Gorham; Angelo | Assessments | N/A | Jennifer Howard | The EPS transaction report will include all transactions made against the payment account with a column to indicate what type of transaction it was (refund, assessment, etc) and another column to specify the type of assessment. The report can then be filtered by "Transaction type" or "Assessment Type" and date etc. | Resolved
34 | Question | 2016-01-14 | How long will information be archived? Can we define and standardize this between other USPS systems? | John W | General | N/A | Jennifer Howard | Payment Modernization System will include the previous two years of Payment Modernization System data which will be configurable based on reporting needs | Resolved
36 | Question | 2016-01-14 | Will the CRID associated with a PO Box belong to the user managing the box or does it have to be the box owner's CRID? |  | CRIDs | Release 1 | Ingrid Molinary | All users that want to manage the PO Box must have access to the CRID associated to the PO Box. There will be regular access to ePOBOL and read-only access, which must be approved by the BSA in BCG | Resolved
8 | Enhancement | 2015-10-07 | Are Ghost Permits going to continue to be supported by the new Payment Modernization system? |  | Permits | Release 2 | Jennifer Howard | This is not currently in scope, but this will be taken into consideration for a future release | Resolved
38 | Question | 2016-01-14 | ePOBOL access - need to determine if read only access is possible for opening/closing PO Box, making payment, etc. or is the "all or nothing" the only option |  | PO Boxes | Release 1 | Ingrid Molinary | From BCG there will be 2 levels of access for ePOBOL - regular access and read-only access, which must be approved by the BSA in BCG | Resolved
37 | Suggestion | 2016-01-14 | EPS Reporting issue for PostalOne! - There is a need to include more sorting capabilities (annual , weekly, category, date range etc.) - currently CAPS limits the reporting and searching capabilities (e.g.. Date filters) |  | Reports | Release 2 | Jennifer Howard | Additional sorting capabilities will be included in EPS reporting. Suggestions can be provided after the pilot for additional enhancements | Resolved
41 | Question | 2016-01-27 | Refunds - how will Enterprise Payment impact the current refund proccess? Example: company is required to submit a 3533 today to initiate a paper check. Preference would be have the refund made directly to the Enterprise Payment account. | Tony R | Refunds | Release 1 | Jennifer Howard | A customer can request a withdrawal from the Enterprise Payment Trust Account online and a check will be issued to the customer. | Resolved
42 | Question | 2016-01-27 | Refunds - is there any change to the current timeframe on refunds? |  | Refunds | Release 1 | Elsye Muljono | No - although refunds to EPS will be processed in a shorter timeframe than those that require a paper check. | Resolved
43 | Question | 2016-02-10 | Example B on the Use Case Scenario grid. Will there be a distinction by location? If a customer is using Mail Anywhere and has a CAPS account they may work with multiple MSPs. Would each MSP then see everything or would a distinction be made at the CRID level tied to the permit used for the mailing so an MSP would possibly only see information relevant to what they are mailing? Clarification: the question revolves more around CAPS balance information. Group would like to see examples of how this will work in Enterprise Payment. | Holly Kozlencer | Mail Anywhere | Release 1 | Ashley White | This sounds similar to Use Case #5 in the user role presentation. We don’t currently have any planned restrictions to the data a user can see once granted access to an EPA, so if we follow current scope, a Mail Owner would have to create multiple EPAs and only grant MSPs access to the EPAs they want them to see. | Resolved
44 | Question | 2016-02-10 | When will file formats be discussed as system-wide changes with Enterprise Payment will necessitate development changes for industry (specifically surrounding CAPS and POBOL). Update: A couple of options are being discussed depending on how the migration is handled and what unique ID number is associated with the data at time of migration (not a CRID). | Angelo | Tech Specs | Release 1 | Jennifer Howard | EPS reports will be in a table format and can be exported into Excel, PDF, and CSV files. | Resolved
45 | Action | 2016-03-30 | Are there permits linked to more than one CRID? There is a general sense of confusion about how this linkage is going to occur and how that CRID will be determined. Can we see a schematic explaining how permits and payment accounts are going to be linked? |  |  | Release 2 | Jennifer/ Barbara/ Josefina | Reviewed with user roles at face-to-face 3/1. | Resolved
46 | Action | 2016-03-30 | CRID-Permit-Multiple Bank Accounts: It might also be helpful to see current state (CAPS) next to future state (EPS) as was suggested by a participant. |  |  | Release 2 | Jennifer/ Barbara/ Josefina | Reviewed with user roles at face-to-face 3/1. | Resolved
47 | Action | 2016-03-30 | MailOwner-CRID-EPS-Permit Balance management - how/where will balance checks be performed? The proposed account management based onEPS roles and the CRID-EPS-Permit relationship could present significant complexity for MSPs. | Linda |  | Release 2 | Jennifer/ Barbara/ Josefina | Reviewed with user roles at face-to-face 3/1. | Resolved
48 | Issue | 2016-04-06 | With the elimination of ghost permits, there is an MSP-mail owner scenario that must be addressed as an alternate method for enabling another party to view a mailer's permit activity . | Linda |  | Release 2 | Josefina Cabatu | Reviewed with user roles at face-to-face 3/1. | Resolved
50 | Issue | 2018-04-10 | The permit, city and state are not in the history report. Or the ACH debit is not showing on the details report. This requires 2 separate reports be pulled to reconcile transactions. Another option would be to include the CRID name in the history report. The report already has the location CRID number. | Steve K | Reports |  | Sergiu Gil | IV to provide all of the frequested fields | Resolved
51 | Issue | 2018-06-21 | EPOBOL True-up functionality. You can't allow the box to expire automatically. | John W | EPOBOL |  | Travis Hayes | 2018-11-01 | In Progress
52 | Question | 2018-06-21 | How do you designate payment of BRM to EPS | John W | BRM |  | Travis Hayes | Just link BRM Permit to EPS Account | Resolved
53 | Question |  | Pending Periodicals process, how do I link multiple PP acounts to EPS | John W | Periodicals |  | Travis Hayes |  | In Progress
54 | Question |  | How to delink permits from EPS | John W | Permit Linkage |  | Sergiu | Delinking currently has to be performed via CR through the PostalOne Help Desk | Resolved
55 | Enhancement |  | Commercial Postal store requirements to be completed and shared with the group | MTAC List | General |  | Robin | Functionality coming July 2019 | In Progress
56 | Enhancement |  | Updated reports for Package Platform and the EPS Dashboard to be shared to the group - WG 173 | MTAC List | Reports |  |  | Shared | Resolved
57 | Enhancement |  | Consolidation of PO Boxes capability to be shared to the group - WG 173 | MTAC List | PO Boxes |  | Gary Li | Duplicate with issue 51 | Resolved
58 | Issue |  | Research the Pitney Bowes Reserve issue and how it can be accommodated in the new system | MTAC List |  |  | Sergiu | 7/1 Currently one user is performing a test PB customer in EPS | Resolved | This is specific to certain customers that are working with PB
59 | Action |  | Final Resolution Statement to be completed and sent out for review - WG 173 | MTAC List |  |  | Travis | Resolution statement sent out and reviewed and updated. | In Progress
60 | Action |  | Update roadmap and timeline to the EPS website | MTAC List |  |  | Mike F | Updated 7/1 on PostalPro | Resolved
61 | Action |  | Draft written documentation for pending periodicals process | MTAC List |  |  | Sergiu | Duplicate with issue 53 | Resolved
62 | Action |  | Set up face to face meeting at MTAC to review outstanding questions on EPS | MTAC List | General |  | Sergiu | Completed Face to Face | Resolved
63 | Issue | 2018-09-10 | Peridical Mailers need the ability to have CPP enabled if they are on EPS, currently this option only exists for CAPS | John W | Periodicals |  | Sergiu |  | In Progress
64 | Issue | 2018-09-13 | Need ability to update contact information in EPS accounts. Internal PostalOne! updates when acceptance employee makes change but external PostalOne! and EPS do not update. | John W | EPS |  | Sergiu |  | In Progress
65 | Issue |  | On the EPS 'Mailing Details Report' the 'Number of Pieces' field for a job is inflated.The 'Number of Pieces' for a job is calculated by aggregating all the job detail transaction records for that job.The issue is caused by the fact that number of full service (FS) pieces is counted when it is already included in the other transactions that are part of the job. Workaround: Review information in PO! dashboard - utilizing the Job ID from the EPS 'Mailing Details Report, search for the corresponding statement in the PO! dashboard and the 'Pieces' displayed is the correct number.If the job has multiple statements,there will be a need to expand the job to view the list of statements and then to locate the 'Piece' field in the appropriate statement based on the transaction amount. | USPS | Reports | 03.05.00.00 - 09/23/2018 | Heather |  | In Progress
66 | Issue |  | The 'Retry' micro-debit button should be disabled immediately when there is an ACH Debit return process for an EPS account.The 'Retry' button is currently not being disabled until the end of the day of when the return occurs so customers can resubmit micro debits for verification when they shouldn't be allowed to do so. Workaround: Do not select the 'Retry' micro debit Button | USPS | EPS | 03.05.00.00 - 09/23/2018 | Heather |  | In Progress
67 | Issue |  | When a user is logged out of the EPS system due to inactivity, they receive a Data Tables warning message instead of a timeout or other meaningful notification.This will be updated to say "logged out due to inactivity".This is a display issue only. Workaround :N/A | USPS | EPS |  | Heather |  | In Progress
68 | Issue |  | The value displayed in the 'ZIP of Verification' field on the Commercial Mailing & Shipping details report is displaying the permit zip code Workaround : N/A | USPS | Reports |  | Heather |  | In Progress

## MTAC Items
Assignee | Track | Category | Action Item | Response | Due Date
Heather | Periodicals | Enterprise Payment | Fix EPS slide in MTAC deck to state deposits are accepted at RSS sites only. | Complete - the slide was corrected before the presentation was distributed
Heather | Periodicals | Enterprise Payment | Develop a communication package/letter for ALL permit holders (Mail Owners/MSPs), CAPS account holders, BCG users and PostalOne Helpdesk database. Communication Package to include: *Information on EPS participation and process steps. *EPS fact sheets, FAQs and webinar information. Share the communication package with WG 173 and Steve Smith (Alliance), Tonda Rush (NNA), John Hannigan (CRPA), Jack Widener (Connect) and Matt Morrone (MCMA) for feedback before distribution | Tasks to complete: 1. General communication to alert migration to EPS and post on BCG 2. Instructions to the BME - SOP on talking points: permit information for customers they are responsible for assisting, confirm contact for local BME to take ownership of migration and content 3. Two letters: (1) CAPS customers (non-eVS/non supported products) announcing retirement of CAPS and deployment of EPS in April 2019 including to contact the BME Managers for help (2) Local trust customers for recommendations to move to EPS with features and benefits 4. Data from PostalOne for permit holders (physical and email addresses); list should include CAPS accounts Include factsheet in the letters and link in email of steps below. | 3/30/2018: Internal review
Heather | Periodicals | Enterprise Payment | Schedule a webinar w/National Newspaper Association on the EPS process. | Pritha to own
Heather | Periodicals | Enterprise Payment | Automating Mobile Check Deposit | Deploy check capture after bouncing of check tested (5/1) Automate the sign up process for mobile check deposit (Sergiu to get us a date) | 2018-05-01
Heather | Periodicals | Enterprise Payment | Determine the future of the invitation code as a process step when migrating to EPS. Will the invitation code requirement be automated and, if so, when? | 4/26/18 we are automating the invitation code process such as PO! Helpdesk can issue invitation code ASAP. USPS is training the BMEs to be able to distribute invitation codes and get mailers signed on same day. | 2018-04-26
Heather | Periodicals | Enterprise Payment | Identify the timeframe on the availability of reports in CAPS for both viewing and downloading after the customer switches over to EPS. | Include in FAQ and repost. When does date start? (data is available for 12 months) Sergio will prepare a response. Fact Sheet will be updated. How to do a reversal in a CAPS account? CAPS DEBIT • Permit is CAPS DEBIT • Postage Statement is submitted and finalized (Money is being collected from CAPS) • Permit is now migrated to EPS • Postage Statement is reversed. o If the original transaction is still pending on CAPS side, meaning if the money was not collected yet, we send the reversal to CAPS. o If the original transaction is not pending, meaning the money was already collected, we send the reversal to EPS. CAPS CREDIT and LOCAL TRUST • Permit is CAPS CREDIT or LOCAL TRUST • Postage Statement is submitted and finalized (Money is being collected from CAPS) • Permit is now migrated to EPS • Postage Statement is reversed. o Postal One always sends the reversal to EPS for CAPS CREDIT and LOCAL TRUST
Heather | Marketing Mail | Enterprise Payment | Following MSPs will follow up with their customers to determine if an online permit can be used: Rose F., Lisa W., David S, Holly, Sue & Robert | Layout what is done today and what can be done in the future. Address in FAQ for opening online permits and how to gain access; create factsheet for online permits and share with Lisa before MTAC
Heather | Marketing Mail | Enterprise Payment | Share details on consolidating payment dates for PO Box renewals with WG 173. | Planned to review at the next WG Meeting - CR for July update - review user stories on 5/3/18 ; get date | 2018-05-03
Vicki/Heather | First Class | Enterprise Payment | Provide a date when EPS will be integrated with eVS. | TBD