## 2020-21 Scheduled Issues
Date Added to List | Detected on Date | Item ID | Application | Summary | Module | Priority* | Target Release | Release Notes
2021-03-30 | 2021-03-26 | 14494 | PostalOne! | ETR - External Balance and fees listing displays erroneus fee information | Mailer View Functionality | Should Have | 2021-08-15 | The Business Customer Gateway (BCG) Fee Calendar listing will be updated to accurately reflect the fee payment status and expiration date. Currently, the BCG Fee Calendar incorrectly displays some Business Reply Mail (BRM) permits with outdated information, showing an old expiration date and unpaid status, when in fact the Master BRM permit fee has already been paid. This is a display issue only.
Priority - Updated Values
01-Low = Wish For 02-Med = Could Have 03-High = Should Have 04-Critical = Must Have

## 2020-2021 Unscheduled Issues
Date Added to List | Detected on Date | Item ID | Application | Summary | Module | Priority* | Target Release | Release Notes
2021-04-28 | 2021-04-27 | 1859 | eBilling | CR - Add Date Range Summary report to EPS Customer Portal | Transactional Reports | Wish For |  | EPS will provide a Date Range Summary report to the EPS Customer Portal, similar to the Date Range Summary that was provided on the CAPS Transaction History Report.
2021-04-28 | 2021-04-26 | 14535 | PostalOne! | Containers were not being deleted for some jobs after reversing and deleting | Mail.dat & Mail.XML |  |  | Mail.dat processing will be updated to ensure that containers are consistently deleted from the database when a finalized Mail.dat job is reversed and deleted. Currently, when a mailer reverses and deletes a finalized Mail.dat job, if they then resubmit the job with the same barcodes, there is a possibility that a duplicate barcode error could be incorrectly generated (error code 7106). If users encounter this issue, they should contact the Helpdesk to request assistance with resubmission. Mail.dat error code 7106 is: “For Seamless, the .csm Label: IM Container Or IM Tray Barcode field must be unique within the submitted job and amongst all physical pallets associated to the .seg eDoc Sender CRID value that were finalized within the last 45 days of the Postage Statement Mailing Date.”
2021-04-28 | 2021-04-22 | 1853 | eBilling | CR 1853 - Timed logout notification | Authentification | Should Have |  | The Business Customer Gateway (BCG) EPS module will be updated to display a pop-up window notification when the customer's session has been logged out of the BCG for inactivity. Currently there is no notification when the logout occurs, potentially resulting in customer confusion.
2021-04-28 | 2021-04-22 | 1854 | eBilling | CR 1854 – removal of Spending History from the Dashboard | Transactional Reports | Should Have |  | The Spending History report will be removed from the Dashboard. The spending history information will still be available at the account level on the EPS Account Spending Summary page.
2021-04-28 | 2021-04-22 | 1855 | eBilling | CR 1855 – Add permit zip from the PO Permit API call to the manage permits page | Manage Products/Services | Should Have |  | The Manage Permits page will be updated to include the permit ZIP Code so that customers are aware of the permit location.
2021-04-28 | 2021-04-12 | 1846 | eBilling | ETR 1846 - Inactivity logic change | Manage Payment Account | Should Have |  | The EPS Automatic account closure logic will be updated to include source system transactions as activity on the EPS account. This will prevent automatic closure of the account for inactivity if the customer had any source system transactions.
2021-04-28 | 2021-04-12 | 1848 | eBilling | CR 1848 - Add permit type and permit number column to Transaction History Report | Transactional Reports | Should Have |  | New columns will be added to the Transaction History Report for Permit Type and Permit Number.
2021-04-28 | 2021-04-12 | 1849 | eBilling | ETR 1849: Utilize Processing checkpoints in transaction processing to help mitigate simultaneous processing | Process Transactions | Must Have |  | Transaction processing will be updated to implement checkpoints to detect and prevent the scenario that is currently creating erroneous duplicate transactions. Under certain rare conditions, two simultaneous transactions can both complete processing. The updated checkpoint logic will identify and correct for those conditions.
2021-04-28 | 2021-04-12 | 1847 | eBilling | CR 1847 - Add Account number dropdown to Transaction History Report | Transactional Reports | Should Have |  | The EPS Transaction History Report will be updated to include a drop-down menu for EPS Account Number selection to accommodate customers with multiple EPS accounts.
2021-02-01 | 2021-01-15 | 1801 | eBilling | ETR 1801 - Processing animation disappears on report pages | Transactional Reports |  |  | EPS Transactional reports will be updated to ensure that the "Processing…" animated messaging remains visible to users when they make a change to a report filter after their initial request.
2020-12-15 | 2020-12-07 | 14301 | PostalOne! | Remove validation from Postal Wizard and Manual Submissions for 3541 Periodical DDU/5-Digit pieces |  |  |  | For Postal Wizard and manual exceptional dispatch Periodicals submissions containing low-volume 5-digit bundles (e.g., newspapers), validation will be updated to remove a restriction that is currently generating an error. The validation is expecting these Destination Delivery Unit (DDU) submissions to claim Carrier Route or 5-Digit rates for the in-county pieces in section A; however, this check should not occur when the pieces are in 5-digit bundles. As a result of this issue, impacted mailers are charged in-county rates for the pieces. Note: This validation update only impacts Postal Wizard and manual submissions; the validation check is not present in Mail.dat/Mail.XML submissions.
2020-12-15 | 2020-11-18 | 1765 | eBilling | ETR 1765 - Portal Commercial Mailing and Shipping Details report Excel is blank | Transactional Reports | Should Have |  | The Commercial Mailing and Shipping Details report download functionality will be updated to ensure that all report results reflected online can be downloaded to Excel. Currently, the Commercial Mailing and Shipping Details report is sometimes blank (except for column headings) when downloaded to Excel through the portal.
2020-10-06 | 2020-09-29 | 1733 | eBilling | CR 1733 - Provide Mailers the ability to hide permits that were closed/cancelled/Delete/inactive status | Miscellanous eBiling Customer Reports | Must Have |  | Functionality will be provided to enable mailers to hide permits that have been closed, cancelled, deleted, or changed to inactive status so that they do not appear in reports or graphics for the mailer. The option to hide permits will be available on the Manage Permit page only for permits that are closed, cancelled, deleted, or inactive.
2020-10-06 | 2020-09-04 | 1719 | eBilling | ETR 1719 - PDF export of large data set only has headers | Transactional Reports | Wish For |  | The Commercial Mailing and Shipping Report will be updated to ensure that all data results are included in the report when it is exported to a Portable Document Format (PDF) file. Currently, the PDF download of the report is sometimes erroneously created with column headings only and no data.
2020-08-31 | 2020-08-28 | 1711 | eBilling | CR 1711 - Purge inactive payment methods | Manage Payment Methods | Should Have |  | EPS will be updated to purge payment methods if they are unused within the previous 2-year period. Customers will receive notification confirming the payment method deactivation. This update will enable EPS to remain in sync with Global Payment when they deactivate payment methods that have been unused in the past 2 years.
2020-06-15 | 2020-06-09 | 14041 | PostalOne! | Set Low Balances Link Not Working | Administrative Module |  |  | The Manage Permits page will be updated to enable the "Set Low Balance Alert" option to work properly. Currently, the "Set Low Balance Alert" button on the Manage Permits page generates an error when users attempt to use it. As a temporary workaround until the issue is corrected, users can navigate to the Balance and Fees page and use the "Set Low Balance Alert" option from that page.
2020-05-05 | 2020-04-23 | 1650 | eBilling | CR 1650 - Update the Permit Status and Permit CRID Name when EPS retrieves Permits from PO | Manage Products/Services | 01-Low |  | Currently in the Enterprise Payment System (EPS), the Manage Permits page displays the existing linked permits from EPS and the new (not linked) permits from the PostalOne! System for the user's Customer Registration ID(s) (CRID(s)). However, if an existing linked permit status or CRID name is updated in the PostalOne! System, the update does not get replicated in EPS. To address this issue, EPS will add logic to update the permit status and permit CRID name for existing, linked permits so that they stay in sync with the PostalOne! System.
2020-05-05 | 2020-02-28 | 1636 | eBilling | CR 1636 - Update the ACH Micro-Debit Verification page to include a link to Manage Products/Services | Payment Method Creation | 02-Medium |  | A hyperlink will be added to the confirmation page that displays when customers successfully complete micro-debit verification for an Automated Clearing House (ACH) debit payment method. The link will enable customers to navigate directly to the Manage Products/Services page to facilitate their next steps.
2020-05-05 | 2020-02-28 | 1637 | eBilling | CR 1637 - Send an instruction email to customers after micro-debit transactions are initiated | Payment Method Creation | 02-Medium |  | An instructional email will be sent to customers after micro-debit transactions are initiated. The email will explain how to complete micro-debit verification and how to link products and services after the verification process has been successfully completed.
2020-05-05 | 2020-01-16 | 1610 | eBilling | CR 1610 - EPOBOL Box # Update/True-up | Additional Product/Service Reports | 02-Medium |  | The PO Box Number and other updated information from Enterprise PO Boxes Online (EPOBOL) will be sent to the Enterprise Payment System (EPS) for display on customer reports.
2020-04-22 | 2020-03-27 | 1645 | eBilling | CR 1645 - Mailer Negative Balance Communication | eBilling Notifications |  |  | USPS is proposing the development of a capability to send specific communication to mailers when their EPS account balance becomes negative. The proposed functionality would send up to three separate notifications to the mailer at specific intervals, beginning when their account first reaches a negative balance state.
2020-04-22 | 2020-03-05 | 1639 | eBilling | CR 1639 - Add refund reason for refund transactions | Process Transactions | 01-Low |  | For refund transactions, an optional reason is proposed to be added, so that the reason for the refund can be captured. This is proposed for Package Platform transactions but may apply for other source systems as well. The refund reason would be provided to Package Platform Data Services so that it would be available for EPS customers through the Informed Visibility-Mail Tracking and Reporting (IV-MTR) data feed.
2020-01-15 | 2020-01-06 | 13788 | PostalOne! | Create a message on the fee renewal letter so that I can understand why I owe a permit fee |  |  |  | The PostalOne! System Fee Renewal letter will be updated to clarify the payment of annual permit fees. When a customer’s Full-Service eligibility percentage for permit mailings falls below the 75% Full-Service threshold, the Fee Renewal letter will include the message: “When a permit falls below the Full-Service threshold at any point after the anniversary date has passed, the annual permit fee is due regardless of whether it goes over the threshold in the future. Once the fee is paid the percentage is reset to zero.”
Priority - Updated Values
01-Low = Wish For 02-Med = Could Have 03-High = Should Have 04-Critical = Must Have

## Closed & Fixed Issues
Date Added to List | Detected on Date | Item ID | Application | Summary | Module | Priority* | Target Release | Release Notes
2021-04-26 | 2021-04-26 | 14534 | PostalOne! | Mail.XML eDoc processing backed up due to locking sessions [INCIDENT# 5875613] | Mail.dat & Mail.XML |  | implemented 4/26/2021 | An issue resulting from auto-finalization and seamless validation updates implemented in the April 25, 2021 PostalOne! System release was corrected. The issue caused seamless postage statements to log large numbers of extraneous validation messages for Mail.XML PostageStatementCreateRequest submissions in a short amount of time, delaying the processing time for all Mail.XML submissions.
2021-03-30 | 2021-03-04 | 1824 | eBilling | CR 1824 - Portal Report Generation Enhancements | Transactional Reports | Should Have | implemented 4/25/2021 | The Transaction History Report and the Commercial Mailing & Shipping Details Report will be updated to enable mailers to select their preferred date ranges prior to the automatic display of data. The reports will no longer auto-load data based on the default search; instead, a “Generate” button will be added so that users can first select their preferred date range, and then generate the report based on that criteria. This will save the time it takes to automatically load the default data, enabling users to get to their search results more quickly.
2021-03-01 | 2021-01-29 | 14415 | PostalOne! | ETR 14415 EPS Permit Error for Fee Payment | Interface |  | implemented 4/25/2021 | The PostalOne! System Balance and Fees functionality will be updated to properly handle date formats. Currently, for some permits linked to Enterprise Payment System (EPS) accounts, the format of the permit fee due date is not recognized. As a result, the fees that are due are not showing up on the Balance and Fees page for those permits.
2021-01-19 | 2021-01-13 | 14370 | PostalOne! | SST – EPS accounts that converted from CAPS encountering error [INCIDENT# 05610114] | Self Service | Must Have | implemented 1/24/2021 | The Self-Service Terminal (SST) application will be updated to properly handle account numbers for Enterprise Payment System (EPS) accounts that have been converted from the Centralized Account Processing System (CAPS). Currently, an error is generated that prevents users from using the SST to check in statements paid using an EPS account that was converted from CAPS. The SST balance check logic for EPS accounts is not properly handling the format of the converted account number. As a temporary workaround until the issue is resolved, mailers can have impacted statements finalized by a BMEU clerk.
2021-01-19 | 2021-01-12 | 14369 | PostalOne! | Seamless eDoc statements with EPS accounts not auto-finalizing during the first attempt [INCIDENT# 0560857] | Domestic Postage Processing |  | implemented 1/24/2021 | Seamless processing will be updated to eliminate an error that is currently preventing some statements from being auto-finalized. Currently, Seamless eDoc postage statements being paid with an Enterprise Payment System (EPS) account are failing to auto-finalize on the first attempt due to an error. As a result, the impacted statements are set to status “UPD” and remain in pending status until they are auto-finalized on the next attempt, which may be up to one hour later. As a temporary workaround until the issue is resolved, impacted statements can be manually finalized. Upon resolution of the issue, auto-finalization processing will be reset to run on the regular 6-hour cycle instead of the current 1-hour cycle that was temporarily implemented to alleviate backups.
2021-01-19 | 2020-11-23 | 1772 | eBilling | ETR 1772 - Ensure Primary Payment Methods suspended through the admin console due to being purged from GP after 2 years of inactivity can be removed from primary priority by customer | Manage Payment Methods | Must Have | implemented 1/24/2021 | EPS portal functionality will be updated to recognize and properly account for the scenario in which a primary payment method has been suspended for inactivity but is not removed as the primary priority in the system. Currently, an issue exists that can result in accounts incorrectly having multiple primary payment methods, even though only one of those methods is active.
2020-12-01 | 2020-11-20 | 14271 | PostalOne! | ETR - Mail.dat - Reinstate Referential Integrity Validations | Mail.dat & Mail.XML | Could Have | implemented 4/25/2021 | Mail.dat referential integrity validation errors 3604 and 3605 will be reinstated with this release in order to check for correct alignment of record counts across the various files associated with an eDoc submission. These validations have no impact on postage calculation. • Mail.dat validation error 3604 – Referential Integrity Error: The Total Number of Copies from all .csm child handling unit records must equal the .csm parent record’s Number of Copies. • Mail.dat validation error 3605 – Referential Integrity Error: The Total Number of Pieces from all .csm child handling unit records must equal the .csm parent record’s Number of Pieces. NOTE: Requires new Mail.dat client 52.1.0.0_PROD.
2020-11-17 | 2020-11-17 | 14262 | PostalOne! | Auto-fin not checking MT/PC additional postage permit balance to enforce negative balance threshold | Domestic Postage Processing | Should Have | implemented 4/25/2021 | For statements in which a Metered or Precancelled Stamp permit is used to pay additional postage for a seamless mailing, the auto-finalization process will be updated to ensure that the permit balance is consistently checked against the negative balance threshold prior to finalization. Currently, some statements in this scenario are being finalized even though the negative balance threshold is exceeded.
2020-11-17 | 2020-11-05 | 14254 | PostalOne! | Statement of Ownership - items that need to be corrected in another release | BMEU |  | implemented 1/10/2021 | The Statement of Ownership upload and submission functionality will be updated to resolve several issues, as described below. • For addresses uploaded via Excel, an error will no longer appear when users attempt to edit or delete an address. The page logic will be revised to upload the corrected addresses again to eliminate the issue. • Holder addresses will be ignored if they are uploaded when "None" is selected. Users should not upload addresses with the "None" option selected. • Issues with usage of the checkbox in determining how to populate the holder addresses will be corrected. • The page form will properly account for and display addresses that are uploaded with state abbreviations having more than 2 characters. Invalid state abbreviations will be corrected by the Address Management System (AMS). • Display of Address Line 2 will be corrected. • Functionality for the Electronic Copies checkbox will be corrected. • Functionality for the "Save as Final" option will be updated to ensure population of the Signature and Title fields.
2020-11-17 | 2020-10-29 | 14243 | PostalOne! | ETR - EIN - Update Shipping Summary Report to display Containers on tray-based copal submission | Mail.dat & Mail.XML | Could Have | implemented 1/10/2021 | The Shipping Summary Report will be updated to display containers for tray-based co-palletized eDoc submissions. Currently, containers are not reflected on the report for tray-based co-palletized mailings. In addition, an update will be made to consistently display the Shipping Summary Report when users access the report by drilling down from the Dashboard.
2020-11-04 | 2020-09-11 | 1725 | eBilling | ETR 1725 - Ensure suspend account is reactivated when simultaneous deposits are made to bring the account's trust balance back to zero. | Process Transactions | Must Have | implemented 1/10/2021 | Timing logic will be adjusted for the account verification and activation process so that suspended accounts for which multiple deposits are received simultaneously can be properly reactivated if the sum of the deposits would bring the negative balance above $0.00. Currently in this scenario, the suspended account is unable to be activated automatically and must be done manually by an administrator.
2020-10-20 | 2020-09-29 | 14203 | PostalOne! | ETR - Mail.dat & Mail.XML - Adjust Size Limit when too many MIDs fail ID promotion | Mail.dat & Mail.XML | Could Have | Implemented 11/15/2020 | Mail.dat and Mail.XML processing will be updated to decrease the number of Mailer IDs (MIDs) that are listed in the error description dynamic value for failed Informed Delivery (ID) promotion incentives. This revision will prevent an error that can occur when there are too many failed MIDs for the available list size. Since the issue occurs after the postage statement has been generated, the statement can successfully finalize, but the eDoc process cannot progress beyond the point of the error to apply incentives. As a result, some ID incentive discounts are not properly applied to Mail.dat and Mail.XML postage statements before they are finalized. As a temporary workaround until the issue is resolved, users can ensure their mailings do not have ID incentive errors for the following scenarios. • Mail.dat Error Code 7269 Description - There is an invalid combination of campaigns entered for this mailing. MID-based campaigns (MID(s): xxx…) cannot be mixed with Serial-based campaigns (MID(s): zzz… ) on an individual statement. • Mail.XML Error Code 9783 Description - There is an invalid combination of campaigns entered for this mailing. MID-based campaigns (MID(s): xxx…) cannot be mixed with Serial-based campaigns (MID(s): zzz… ) on an individual statement.
2020-10-20 | 2020-09-16 | 1727 | eBilling | CR 1727 - BNS 5272/5273 - PTR Premium Data Transactions - Phase I | Process Transactions | Should Have | Implemented 11/8/2020 | EPS will process Product Tracking and Reporting (PTR) Premium Data transactions for VeriPoint and ExD services and will include those transactions on the Transaction History Report, the Dashboard, and the Account Spending History Report in the appropriate categories.
2020-10-20 | 2020-07-09 | 1673 | eBilling | ETR 1673 - Correctly Populate the Processing Category for Periodicals Mail | Process Transactions | Should Have | Implemented 11/8/2020 | For Periodicals, the Processing Category field will be populated so that it is properly included in the EPS Postage Statement drilldown reports. In addition, the Processing Category for Periodicals will be sent to Package Platform Data Services, which will enable missing data elements to be provided in the Informed Visibility Mail Tracking and Reporting (IV-MTR) data feed.
2020-10-20 | 2020-05-08 | 13986 | PostalOne! | Problem Summary: Missing/Incorrect Data in PP IV Feed for 3541 Periodical Statement | Interface | Medium | Implemented 11/15/2020 | With this release, the Informed Visibility Mail Tracking and Reporting (IV-MTR) data feed will include additional data elements for Periodicals postage statements. The counts for bundles, pallets, and sacks will be included, along with the Processing Category. These data elements are currently not populated in the IV-MTR data feed for Periodicals postage statements.
2020-10-06 | 2020-09-13 | 1726 | eBilling | ETR 1726 - EPS Admin Console - error message displays on users and roles tab when logged in as custome (payment manager and subscribers only)r or CSRL as Admin Console | Admin Console | Could Have | Implemented 11/8/2020 | The User/Roles tab of the Account Management page will be updated so that an error message is not displayed for Payment Manager or Subscriber users when they access the page.
2020-10-06 | 2020-09-01 | 1713 | eBilling | ETR 1713 - Report filters are not persisted in export data | Standard Report Functionality | Should Have | implemented 1/10/2021 | Report export functionality will be updated to retain any filters that the user has selected while viewing the report prior to exporting to an external file (PDF, .xls, .csv). Currently the export function exports the entire dataset containing the report results, even if the user has filtered the result selection to view only a subset of the results. As a temporary workaround until the issue is resolved, users can apply filters as needed to the export file.
2020-10-06 | 2020-07-21 | 1679 | eBilling | ETR 1679 - Unable to assign users and roles for EPAs to user that has been granted EPS access for a CRID | Manage Payment Account | Must Have | Implemented 11/8/2020 | A page caching issue will be corrected to enable administrative users to consistently assign users and roles for Enterprise Payment System (EPS) accounts. Currently, for some new EPS accounts to which access has been granted for a particular user, the administrative user is unable to assign a role to the new user so that they can manage the account. The issue occurs because new users granted access to EPS in the Business Customer Gateway (BCG) do not show up on the page for the administrative user right away if the admin user is already positioned in the User/Roles tab.
2020-09-21 | 2020-09-10 | 14181 | PostalOne! | ETR - Mail.dat - Update MDX to Push 100% of Mail.dat ZIP files to IV | Mail.dat & Mail.XML | Must Have | Implemented 10/4/2020 | With this release, updated Mail.dat client 51.3.0.0_PROD will be required in order to correct an issue that is currently preventing the PostalOne! System from successfully sending compressed Mail.dat ZIP (.zip) files to Informed Visibility (IV). The compressed files provide visibility of critical analytics and mail conditions that are essential to Postal Operations. The defect, which was introduced in the August 23, 2020 PostalOne! System Release, impacts Mail.dat compressed file naming. As a result, the PostalOne! System is unable to transfer the compressed files to IV. Note that this issue impacts 6% of the data files transferred between the PostalOne! and IV systems. Prior to implementation of the new Mail.dat client, the impacted files are being manually transferred so that they are available in IV. NOTE: There are no validation updates associated with this change.
2020-09-21 | 2020-08-27 | 1708 | eBilling | ETR 1708 - EPS reports do not export in default descending transaction date/time order | Standard Report Functionality | Wish For | Implemented 11/8/2020 | For reports that are exported to a selected file format for download, the default sort order for the export file will be standardized so that the most recent transactions are at the top (i.e., descending transaction date and time order). Currently, some report extract files are sorted with the oldest transctions at the top instead (ascending order).
2020-08-31 | 2020-08-27 | 14160 | PostalOne! | ETR - Closing of additional entry office permits when there is inactivity for 18 months should not close the permits at the original entry offfice | Periodicals | Must Have | implemented1/10/2021 | The PostalOne! System will be updated to correct an issue with deactivation of Periodicals permits following 18 months of inactivity. Currently, deactivation of a Periodicals additional entry office permit due to inactivity is also incorrectly deactivating the permit from the original entry office. As a result, when a mailing is submitted to an original entry office on one of the impacted permits, the mailing is rejected until the permit is reactivated by USPS personnel. The updated logic will prevent the deactivation of a Periodicals permit from the original entry office due to inactivity; it will only be deactivated from the additional entry office.
2020-08-31 | 2020-08-25 | 1706 | eBilling | ETR 1706 - external for commercial mailing and shipping details report with 78K rows of data, the excel export returns a file with column headers and no data | Standard Report Functionality | Could Have | implemented 9/13/2020 | The Commercial Mailing and Shipping Details Report export functionality will be updated to properly reflect all data matching the report criteria. Currently, attempts to export the report result in an export file containing column headings only (i.e., no data), even though all data is properly reflected on the online report page in EPS.
2020-08-31 | 2020-08-21 | 14144 | PostalOne! | Mail.dat postage statements fail to populate postage statement details on the BCG dashboard for mail owners | Mail.dat & Mail.XML |  | implemented 1/10/2021 | Mail.dat processing will be updated to consistently populate postage statement details on the Business Customer Gateway (BCG) Dashboard for mail owners. Currently, the mail owner is unable to view details of a Mail.dat submission where the permit holder and mail owner have the same Customer Registration ID (CRID) but that CRID is different from the mailing agent who submits the mailing. In this scenario, the mailing agent (eDoc submitter) is able to view the statement details, but the mail owner and permit holder cannot, even though the mailing submission is populated on their BCG Dashboard, and they should have access to the statement details.
2020-08-31 | 2020-08-19 | 14136 | PostalOne! | Regression Automation: After override permit with no funds, Mailer statement is displayed as pending cancellation at Postal Wizard | Postage Statement Wizard |  | implemented 1/10/2021 | The Postal Wizard will be updated to eliminate an issue that results in postage statements that are finalized sometimes showing up on the Business Customer Gateway (BCG) Postal Wizard Dashboard with an incorrect status of "Pending Cancellation".
2020-08-31 | 2020-08-14 | 14129 | PostalOne! | BCG PostalWIzard Mail Owner Account Search returns no results when seraching by Account No + Permit No + Permit Pub Type | BCG |  | implemented 1/10/2021 | The Business Customer Gateway (BCG) Postal Wizard Account Search functionality will be updated to properly return results when searching by Account Number, Permit Number, and Permit Pub Type. Currently, the Account Search functionality is unable to retrieve any results when Mail Owners attempt to search for a specific permit using the combination of all three attributes (Account Number, Permit Number, and Permit Pub Type). However, the permit is included in the data results returned when Mail Owners search using only the Account Number.
2020-08-04 | 2020-07-30 | 1682 | eBilling | ETR 1682 - Performance improvement on EPS report export functionality | Standard Report Functionality | Should Have | Implemented 8/30/2020 | Performance will be improved for the Enterprise Payment System (EPS) report export functionality to enable users to export a larger number of records in one operation. Currently, when users attempt to export reports that have a long date range (i.e., large number of result records), the action times out before completion. As a temporary workaround, users can piece together the export results from several smaller date ranges to cover the timeframe needed for monthly reconciliation.
2020-08-04 | 2020-07-27 | 14100 | PostalOne! | The client error SEV4 is being thrown due to parsing issue of date formatter | Mail.dat & Mail.XML |  | implemented1/10/2021 | Mail.dat logic will be updated to properly parse the date for Mail.dat submissions where the uploading computer is set to use a locale other than English (United States). Currently, when Mail.dat files are uploaded from a computer with the locale (region) set to French (Canada), the Mail.dat client is unable to parse the date format and generates a system error. As a temporary workaround until the issue is resolved, users can change their region to English (United States) to prevent the error.
2020-08-04 | 2020-07-24 | 1681 | eBilling | CR 1681 - Send Filtered Mail Class to PPC Data Services |  | Could Have | implemented 4/25/2021 | EPS will update the interface with Package Platform Data Services to include the mail class for EPS transactions processed from the PostalOne! System. This will enable EPS customers to view the mail class for those transactions within their EPS Informed Visibility – Mail Tracking and Reporting (IV-MTR) commercial mailing data feed. This will provide greater transaction detail visibility and reduce the need for mailers to contact the Helpdesk for this information.
2020-08-04 | 2020-07-23 | 14097 | PostalOne! | SST incorrectly indicating that EPS account has insufficient postage | Domestic Postage Processing | Should Have | implemented1/10/2021 | The Self-Service Terminal (SST) logic will be updated to correctly evaluate whether a statement's permit has a sufficient balance in the linked Enterprise Payment System (EPS) account for the postage. Currently, for some submissions, the SST incorrectly indicates that the EPS account has insufficient postage. The issue occurs when an EPS permit is used to pay additional postage for a statement that was initially created using a non-EPS permit. As a temporary workaround until the issue is resolved, SST users can have a clerk finalize the statement.
2020-08-04 | 2020-07-01 | 14074 | PostalOne! | Mail.dat – ETR – Receipts – Batch Processing - Include File Name of eDoc when MDRFileLoad expected files validation throws | Mail.dat & Mail.XML | Could Have | Implemented8/23/2020 | Mail.dat batch processing will be updated to populate the file name of the eDoc in the Mail.dat receipt for cases where the file load (via batch processing) results in a “missing file” error (i.e., MDRFileLoad expected files error). Currently, the check for missing files occurs prior to the point at which the file name is captured for population in the Mail.dat receipt. With this update, the process will populate the Mail.dat receipt file name using the file name from the header file (.hdr), alleviating the issue and enabling the file name to be included even when the “missing files” error is generated. This applies to all receipt types (ASCII, XML, and EXML).
2020-07-20 | 2020-02-26 | 13871 | PostalOne! | ETR User Not Authorized for Specail Nonprofit Prices | Interface | 02-Medium | Implemented8/23/2020 | For Periodicals postage statements, the process for creation of Additional Entry offices will be updated to implement logic that will check the Periodicals database for the rate authorization and assign it accordingly. Currently, some Periodicals statements submitted at new Additional Entry offices incorrectly receive special nonprofit pricing when they are authorized only for regular outside-county rates.
2020-06-30 | 2020-06-30 | 14070 | PostalOne! | Mail.dat seamless submissions incorrectly change postage when mailer mailing date is updated | Mail.dat & Mail.XML |  | Implemented 10/4/2020 | Mail.dat processing will be updated to properly account for the scenario where a seamless postage statement submission with a future mailing date (post-price-change effective date) undergoes a mailing date change in the Business Customer Gateway (BCG). Currently for this scenario, if the mailing date is changed to a pre-price-change date, the postage amount is incorrectly charged.
2020-06-30 | 2020-06-12 | 14046 | PostalOne! | Cost Center does not populate for auto-fin FPP statements | Domestic Postage Processing | Should Have | Implemented 8/23/2020 | For Centralized Postage Payment (CPP) Periodicals, an issue will be corrected to populate the cost center in order to enable the postage statement to complete auto-finalization. Currently, when the PostalOne! System attempts to finalize a CPP Periodicals statement as part of the auto-finalization process, the cost center is not populated. As a result, the statement is stuck in a pending status. As a temporary workaround until the issue is resolved, mailers can submit the job with a future mailing date and then request that the clerk manually finalize the mailing. This will populate the cost center and allow the finalization to complete.
2020-06-30 | 2019-11-08 | 13678 | PostalOne! | BCG Postal Wizard printer friendly confirmation page opens up as a .cfm extension on google chrome | Postage Statement Wizard | 01-Low | Implemented 8/23/2020 | The PostalOne! System Postal Wizard will be updated to properly print the Printer-Friendly version of the postage statement confirmation page. Currently, when Business Customer Gateway (BCG) users attempt to print the Printer-Friendly version of the confirmation page after completing a postage statement submission in the PostalWizard, if they are using the Google Chrome™ browser, the page converts to a ColdFusion Markup (.cfm) file type instead of a Portable Document Format file (.pdf). As a result, the page cannot be printed or saved. As a temporary workaround until the issue is resolved, users can save the file in Portable Document Format (PDF), or print the confirmation page using a different browser.
2020-06-18 | 2020-06-15 | 14048 | PostalOne! | ETR - Mail.dat - SEV2 error throwing when eDoc verification facility is not BMEU | Mail.dat & Mail.XML | Should Have | Implemented 6/28/2020 | Mail.dat validation will be updated to properly handle submissions of Mail.dat Mail Piece Unit (MPU)/Component Relationship (.mcr) files where the Segment File eDoc Verification Facility ZIP Code maps to a non-BMEU facility. Currently, when a BMEU facility type record does not exist for the eDoc Verification Facility lookup, a “SEV2” system error is generated. This occurs during validation of Mail.dat Mail Piece Unit (MPU)/Component Relationship (.mcr) files. An updated optional Mail.dat client (51.0.1.0_PROD) is available to resolve this issue.
2020-06-15 | 2020-06-09 | 14039 | PostalOne! | ETR Value for affixed postage on FC postage statements is not being provided to EPS | Interface |  | implemented 4/25/2021 | The PostalOne! System interface with EPS will be updated to provide the value for affixed postage on First-Class Mail postage statements after they are finalized. Currently, this value is missing in the additional transaction details that are provided to EPS through this interface. The issue does not impact postage.
2020-06-02 | 2020-05-17 | 14004 | PostalOne! | ETR - Fee Due Date e-mail notification uses incorrect Due Date | Mailer View Functionality |  | Implemented 7/26/2020 | The PostalOne! System Fee Payment notification process will be updated to properly evaluate the fee due date when sending email messages to mailers once their Fee Waiver period ends. Currently, when a mailer’s Fee Waiver ends, the Fee Payment notification process is not retrieving the correct fee due date. As a result, some mailers can receive Fee Payment notifications stating an incorrect fee due date that is sooner than it should be.
2020-05-05 | 2020-04-27 | 13968 | PostalOne! | International statements in Rework status should not be sent to EPS | Int'l Postage Processing | 02-Medium | Implemented 8/23/2020 | International postage statement processing will be updated to match domestic statement processing which does not allow statements in Rework status to be sent to EPS. Currently, International statements in Rework status can incorrectly be sent to EPS.
2020-05-05 | 2020-04-27 | 13967 | PostalOne! | ETR 13967 Inactive Time Warning - Attn Required | Interface | 02-Medium | Implemented 6/14/2020 | The PostalOne! System session inactivity timeframe will be changed to 15 minutes. Starting with a 10-minute period of inactivity, up to 3 warning messages will be displayed to the user (at 10, 13, and 15 minutes of inactivity). If no session activity has occurred during the 15-minute warning period, the user will be logged out.
2020-05-05 | 2020-02-10 | 13849 | PostalOne! | Balance and Fees – Encode user_id value in API call to EPS in the URL | Administrative Module | 02-Medium | resolved & closed 1/26/2021 | The Balance and Fees page module will be updated to properly account for certain special characters (such as an ampersand ("&")) in the User ID. This will allow mailers with these special characters in their User ID to pay their permit fees in the Balance and Fees application. Currently, some mailers are unable to pay their permit fees on the Balance and Fees page using their EPS account due to the module's inability to recognize special characters in the User ID.
2020-05-05 | 2020-01-16 | 1606 | eBilling | CR 1606 - Add an export option on Manage Permits page | Manage Products/Services | 01-Low | implemented 4/25/2021 | Standard export options will be added to the Manage Permit page with this release. This will enable mailers to export their permits to a Portable Document Format (.pdf) file, comma-separated values (.csv) file, or an Excel worksheet (.xls) so that they can more easily filter and review their permits that are linked to EPS accounts. When the Export option is clicked, EPS will export all permits based on the filtered search results to the selected file type.
2020-04-22 | 2019-10-03 | 13594 | PostalOne! | Update handling of fee reversals for EPS accounts to account for more fee types | Fee Transactions | 02-Medium | Implemented 6/14/2020 | For Enterprise Payment System (EPS) accounts, the process for handling reversals of fee payments in the PostalOne! System will be updated to enable additional fee types to be reversed. Currently, clerks are unable to reverse some fees if they were paid prior to an account being converted to EPS.
2020-04-08 | 2020-04-01 | 13933 | PostalOne! | ETR - Mail.dat - Update Customer Reference ID Output to Postage Statement | Mail.dat & Mail.XML | 02-Medium | Implemented 8/23/2020 | Mail.dat processing will be updated to properly populate the Customer Reference ID on postage statements. Currently, Mail.dat uses the Mailpiece Unit (MPU) ID to retrieve the data with which to populate this field. However, the MPU ID is not always a unique identifier, sometimes resulting in an incorrect Customer Reference ID being populated on the postage statement. This can occur when the Mailer Postage Account (.mpa) permit pairs both reference the same MPU ID in the MPU/Component Relationship record (.mcr), even though the Segment file (SEG) ID is different. The Mail.dat mapping process will be updated to use a combination of SEG ID and MPU ID to populate the field, which will ensure that the correct Customer Reference ID is retrieved, since the SEG ID + MPU ID combination is always unique. As a temporary workaround until the issue is resolved, mailers can update their data to ensure the MPU IDs are unique.
2020-04-07 | 2020-01-28 | 1624 | eBilling | CR 1624 - Add Mail Class Mapping for New Package Platform Mail Class Codes | Additional Product/Service Reports | 01-Low | Implemented 6/14/2020 | The Commercial Mailing and Shipping Details Report and the Spending History Reports (dashboard and account levels) will categorize new Package Platform products into the following categories:
2020-04-07 | 2020-01-22 | 1618 | eBilling | CR 1618: Add Description for PO Product Types MY and YR | Transactional Reports | 01-Low | Implemented 6/14/2020 | To accommodate the updated International Postage Statement format, the following two values will be added to the list of possible values for the Description column on the EPS Transaction History Report: "International Postage Statement Part R", corresponding to PostalOne! System Product Type Code "MY", and "International Postage Statement Reversal Part R", corresponding to PostalOne! System Product Type Code "YR". These descriptions will be visible for customers who have these types of postage statement transactions through the PostalOne! System.
2020-04-07 | 2019-11-22 | 13703 | PostalOne! | BCG Dashboard does not open when username has more than 1000 permits | BCG | 02-Medium | Implemented 6/14/2020 | The Business Customer Gateway (BCG) Dashboard will be updated to enable the page to properly handle user accounts that have more than 1000 permits. Currently, the page does not display if the user has more than 1000 permits. The page logic is incorrectly attempting to load alerts for each of the permits, which causes it to time out.
2020-03-24 | 2020-03-23 | 13922 | PostalOne! | Timestamp error on fee payments screens on OMAS permits that do not have an account number populated | Fee Transactions |  | Implemented 6/14/2020 | The PostalOne! System will be updated to eliminate a timestamp error that is currently generated On the Fee Payment page for Official Mail Accounting System (OMAS) permits that do not have an account number populated.
2020-03-24 | 2020-03-09 | 13892 | PostalOne! | Postal Wizard 3541 Periodical Error Due to Subscriber Copy Rates | Postage Statement Wizard | 02-Medium | Implemented 6/14/2020 | The Postal Wizard will be updated to correct an error that currently occurs when a user submits a consolidated Periodicals postage statement (PS Form 3541) through Postal Wizard. Following the Line Item Entry page, a generic error occurs which prevents the statement from being submitted. The error is a result of a defect in the calculation of the Subscriber Pound Rates. As a temporary workaround until the issue is resolved, mailers can have the clerk enter a manual hard copy submission for them.
2020-03-24 | 2020-02-28 | 1634 | eBilling | ETR 1634 – Increase the length of allowed digits for Customer Number for AEC customers | Manage Products/Services | 02-Medium | Implemented 6/14/2020 | The Enterprise Payment System (EPS) portal will be updated to increase the field size for entry of the Customer Number to allow up to 7 digits. This will enable Address Element Correction (AEC) and Address Change Service (ACS) customers to use the portal to link their AEC/ACS accounts to their EPS accounts so that they can pay for AEC/ACS Address Quality services using their EPS accounts. Currently, the Customer Number entry field does not accommodate the 7-digit maximum length of AEC/ACS Customer Numbers. As a result, AEC/ACS customers cannot link to their EPS accounts and must contact the Helpdesk to have this done manually for them through a scheduled back-end process.
2020-03-24 | 2020-02-26 | 13871 | PostalOne! | ETR User Not Authorized for Specail Nonprofit Prices | Interface | 02-Medium | Implemented 6/14/2020 | For Periodicals postage statements, the process for creation of Additional Entry offices will be updated to implement logic that will check the Periodicals database for the rate authorization and assign it accordingly. Currently, some Periodicals statements submitted at new Additional Entry offices incorrectly receive special nonprofit pricing when they are authorized only for regular outside-county rates.
2020-03-24 | 2020-02-06 | 1628 | eBilling | ETR 1628 - incorrect Filtered Mail Class mapping for PO transactions | Process Transactions | 02-Medium | Implemented 6/14/2020 | EPS processing will be updated to properly map transactions to the mail class of the specific postage statement transaction when mapping transaction data used for reporting. Currently, many PostalOne! System transactions paid through the Enterprise Payment System (EPS) are incorrectly being mapped to the default mail class instead of the mail class associated with the postage statement for that particular transaction. The issue impacts EPS customer reports that are sorted by mail class, since they may show a different mail class than the one associated with the postage statement for the transaction(s) on the report. The Filtered Mail Class field that is mapped incorrectly is only used by EPS for reporting; not for transaction invoicing.
2020-03-18 | 2020-03-17 | 13908 | PostalOne! | ETR Auto Fee Renewal Enhancement | Interface | 02-Medium | Implemented 3/22/2020 | The PostalOne! System Automated Fee Renewal functionality was updated so that it is available only for Qualified Business Reply Mail (QBRM) High-Volume permits that are linked to a valid Enterprise Payment System (EPS) account. Only the QBRM Annual Maintenance Fee (fee type “BA”) and the QBRM Quarterly Fee (fee type “BQ”) permit fees qualify for auto-renewal. The Automated Fee Renewal functionality implemented in a previous PostalOne! System release included all permit fees, causing some customers’ fees to be renewed unexpectedly. Reversals are being generated for impacted customers whose fees were charged unexpectedly. Please note that mailers who had previously opted in for auto-fee payment will need to select “Auto-Fee Renewal” on their QBRM High-Volume permits again to indicate which permits should have their fee auto-renewed.
2020-02-26 | 2020-02-12 | 13856 | PostalOne! | ETR - Mail.dat - Full Service Discount Not Removed from Spoilage | Mail.dat & Mail.XML | 02-Medium | Implemented 6/14/2020 | For Full Service automation saturation letters, Mail.dat processing will be updated to ensure the Full Service discount is applied to mailpieces on the statement that are marked for spoilage. Currently, for Full Service saturation letters (i.e., pieces that are charged the Full Service rate on a postage statement), Mail.dat incorrectly deducts spoilage pieces using the non-Full Service rate, reducing the postage due by a larger amount than it should. Spoilage or shortage occurs in mailings when the mailer finds that one or more pieces identified in their Piece Detail Record (PDR) or Piece Barcode (PBC) file was not actually mailed. (For example, it may have been damaged in sorting machinery.) Resolution of this issue will ensure spoilage adjustments correctly deduct the appropriate amount from the postage statement(s) on which those pieces were paid.
2020-02-05 | 2019-12-20 | 1604 | eBilling | CR 1604 - Update default date range on iCAPS Invoice Management Page | Miscellanous eBiling Customer Reports | 02-Medium | Implemented3/15/2020 | The default date range on the iCAPS Invoice Management page will be updated to be +/- 30 days from the current date. Because this page display filters on the invoice due date, the updated default date range will allow customers to see invoices due in the last 30 days, and any currently open invoices which are still accruing charges and have a future due date.
2020-02-05 | 2018-03-12 | 12205 | PostalOne! | CR - QUAD's request to allow Preliminary statements to be canceled from BCG Dashboard | BCG | 01-Low | Implemented3/15/2020 | The PostalOne! System Business Customer Gateway (BCG) will be updated to allow users to cancel preliminary non-financial estimate statements (“EST” status) from the BCG dashboard. This update will allow users to cancel old “EST” preliminary statements and resubmit eDocs to generate new preliminary statements.
2020-01-22 | 2020-01-07 | 13789 | PostalOne! | eInduction Quick Status Report Search does not accept the hyphen |  | 01-Low | Implemented3/15/2020 | The eInduction Quick Status Report search will be updated to correctly handle a hyphen ("-") character in the Intelligent Mail container barcode (IMcb). The hyphen is an allowable character in the IMcb; however the eInduction Quick Status Report search feature is not able to process it and generates an error stating that the barcode is unidentifable.
2020-01-22 | 2019-12-03 | 13718 | PostalOne! | CR - Mail.dat - Ensure Date Populated in eDoc when corresponding Time populated | Mail.dat & Mail.XML | 02-Medium | Implemented3/15/2020 | Mail.dat will be updated to ensure that the eDoc date is populated when the corresponding time is populated. Currently, an unspecified internal error is generated for some invalid date/time combinations in Mail.dat eDoc that are not covered by the Idealliance® Mail.dat technical specifications. There is currently no corresponding Mail.dat client error to inform the mailer of the reason for the failure. To alleviate this issue, Mail.dat validation will be updated to implement new error code 5057 and to revise existing error code 3702 as shown below. New Error Code 5057 Description: Required Field Missing: Scheduled Induction End Date is a required field in the .csm file when Scheduled Induction End Time is present. Modified Error Code 3702 Description: Required Field Missing: Scheduled Ship Date is a required field in the .csm file when Scheduled Ship Time is present
2020-01-22 | 2019-08-13 | 13482 | PostalOne! | Nonprofit Application Status Code Error for BMEU Users | Interface | 02-Medium | Issue Resolved 1/10/2020 | Nonprofit application processing will be updated to eliminate a system error that currently prevents users from submitting the Application to Mail at Nonprofit USPS Marketing Mail Prices. The following system error displays when users attempt to submit the application: "You must correct the following error(s) before proceeding: Status Code is required". There is no Status Code field available on the application interface since it is an internal field used by back-end processing only. As a result, the application cannot be submitted because the user has no means of correcting the field indicated by the error message.
2020-01-15 | 2020-01-14 | 13799 | PostalOne! | Mail.XML - Update join to allow Master statements to import into SASP | Mail.dat & Mail.XML | 02-Medium | Implemented 1/26/2020 | Mail.XML will be updated to correct an issue introduced in PostalOne! System Release 50.0.0.0 that prevents master postage statements from being imported into Seamless Acceptance and Service Performance (SASP) for downstream processing. Failure of the SASP extracts for these master statements may cause the Mailer Scorecard to display invalid undocumented errors and unlinked co-palletization errors. Any errors generated due to these failures will be removed before January assessments are created.
2020-01-15 | 2020-01-14 | 13798 | PostalOne! | Fee Waiver Calculations - Pre Price | Interface | 02-Medium | Implemented 1/16/2020 | This applies to mailings where 90% or more of Full-Service-eligible mail is presented as Full-Service. The PostalOne! System Full-Service fee waiver eligibility threshold will be reset to zero (0%) for consistency with the fee waiver structure that was in place prior to January 12, 2020 and which will continue until January 26, 2020. A defect introduced in the PostalOne! System Release 50.0.0.0 on January 12, 2020 incorrectly set the fee waiver eligibility threshold to 75%. As a result, some customers’ annual permit fees erroneously appear to become due immediately for mailings that have a Full-Service eligibility percentage less than 75%.
2020-01-15 | 2020-01-14 | 13800 | PostalOne! | Fee Waiver – Remove FS Eligibility Percentage from pay fees checkbox logic for R50.0.0 0 Pre-Price | BCG | 02-Medium | Implemented 1/16/2020 | The Business Customer Gateway (BCG) Balance and Fees page will be updated for consistency with allowance of the Full-Service fee waiver grace period between January 12 and January 26, 2020. During this period, the Full-Service eligibility percentage is not considered in the logic used to determine the fee payment. The checkbox to pay annual fees is only displayed during this timeframe if the 90% Full-Service condition is not met (i.e., 90% or more of Full-Service-eligible mail must be presented as Full-Service).
2020-01-15 | 2020-01-06 | 13787 | PostalOne! | Create a message on the PO! balance and fees screens so that I can understand why I owe a permit fee. |  |  | Implemented 1/26/2020 | The PostalOne! System Balance and Fees page will be updated to clarify the payment of annual permit fees. When a customer’s Full-Service eligibility percentage for permit mailings falls below the 75% Full-Service threshold, the Balance and Fees page will display the message: “When a permit falls below the Full-Service threshold at any point after the anniversary date has passed, the annual permit fee is due regardless of whether it goes over the threshold in the future. Once the fee is paid the percentage is reset to zero.”
2020-01-06 | 2019-12-06 | 13727 | PostalOne! | IMBA Transactions with EPS incorrect rounding | Interface | 02-Medium | Implemented 1/26/2020 | Processing for Intelligent Mail Barcode Accounting (IMbA) transactions will be updated to use proper rounding methodology in order to correct a very small ($0.01) rounding issue currently affecting some IMbA transactions for Enterprise Payment Systems (EPS) accounts.
2019-11-20 | 2019-11-05 | 13663 | PostalOne! | Periodicals can have an incorrect limited circulation/non-profit discount after Weight or Ad% is updated by clerks. | Periodicals | 02-Medium | Implemented 1/12/2020 | Periodicals processing will be updated to consistently calculate the Limited Circulation/Non-profit discount accurately. Currently, if the Weight or Advertising Percentage on a Periodicals statement is updated by a clerk, the statement can have an incorrect Limited Circulation/Non-profit discount. This is due to an error in the logic used when recalculating the Limited Circulation/Non-profit discount following an update to the Periodicals' Weight or Advertising Percentage. In that scenario, if the Periodicals statement claims both a Full Service discount and the Limited Circulation/Non-profit discount, then the latter discount is recalculated incorrectly. This results in a larger discount being applied than should be, which undercharges the mailer for the statement.
2019-11-20 | 2019-10-25 | 1568 | eBilling | ETR 1568 - Show Username, First, and Lastname for users displayed on User Roles Tab to allow multiple users with same first and lastname but different username to be displayed | Authentification | 02-Medium | Implemented3/15/2020 | The User Roles tab on the Manage Accounts page will be updated to show the Username, First Name, and Last Name for users in order to allow multiple users with same first and last name but a different username to be displayed.
2019-11-06 | 2019-10-31 | 13655 | PostalOne! | ETR - Mail.dat The job encountered internal error for Transportation update | Mail.dat & Mail.XML | 02-Medium | Implemented 1/12/2020 | Mail.dat will be updated to eliminate the generation of an internal database error that currently occurs when a user submits a Transportation update file. The error (“PostalOne! encountered an internal error during Edropship processing. This will be automatically re-attempted.”) is generated as the result of a data object storage size mismatch. The re-attempt also fails because the mismatch is unresolved.
2019-11-06 | 2019-10-22 | 13631 | PostalOne! | Mail.dat: the client warning 7194 is thrown incorrectly | Mail.dat & Mail.XML | 02-Medium | Implemented 1/12/2020 | Mail.dat error validation logic will be updated to properly evaluate client warning 7194 for Informed Delivery EST (estimated) submissions with qualifying pieces. Currently in this scenario, warning 7194 is being generated incorrectly: “The .ccr Characteristic provided was {1}. There are no qualifying pieces for the incentive claimed in the postage statement. The discount will not be applied”. As a temporary workaround until the issue is resolved, the warning can be ignored, and mailers receiving the warning erroneously will still be awarded the incentive discount for the qualifying Informed Delivery pieces in the submission. Alternatively, the job can be submitted as Ready-to-Pay or Auto-finalize to avoid the warning altogether.
2019-11-06 | 2019-10-07 | 13603 | PostalOne! | eInduction - Error deactivation page does not include EST containers | eInduction | 01-Low | Implemented 1/12/2020 | The eInduction deactivation page will be updated to include containers with a status of “EST”. The applicable eInduction error (“E28P: Container was associated to a preliminary postage statement (EST status)”) will be displayed as “Unmanifested” for these containers on the deactivation page.
2019-10-23 | 2019-10-18 | 13621 | PostalOne! | Mail.dat - Update EPS Validation to Check Mulitple Accounts in eDoc | Mail.dat & Mail.XML | 02-Medium | Implemented 1/12/2020 | Validation for Mail.dat submissions paid with an Enterprise Payment System (EPS) account will be updated to check for multiple accounts in eDoc. Currently, when multiple accounts exist in eDoc, Mail.dat only sends the first account number to EPS for validation. As a result, every EPS account number linked to the eDoc receives the same validation response as the first account. If the first account is valid, all the accounts pass validation; if the first account fails validation, all the linked accounts fail. Mail.dat error 5023 is incorrectly generated in cases where the first EPS account is invalid, but another account on the eDoc is valid and not checked. Resolution of this issue will enable all accounts on the eDoc to be checked for validity, not just the first account found. Validation error 5023 is: "Payment Account Number {1} does not have an active primary payment method for purchase".
2019-10-23 | 2019-10-03 | 13595 | PostalOne! | Display issue – The date/time is incorrect for the printer friendly version of the confirmation page |  | 01-Low | Implemented 8/23/2020 | The printer-friendly version of the confirmation page will be corrected to display the date and time that the statement was submitted. The current date and time is incorrectly displayed in the printer-friendly version of the page instead of the actual statement submission time. This is a display issue only.
2019-10-23 | 2019-09-22 | 1546 | eBilling | ETR 1546 : Accounts Pending Closure Job should verify all transactions for an ACH Debit Payment Method have been successfully aggregated and sent to Oracle AR before account can be closed | Process Transactions | 03-High | Implemented 1/12/2020 | The Account Pending Closure process and the Close Account process will be updated to verify that all existing transactions made against an Automated Clearing House (ACH) debit payment method have been successfully sent to Global Payment and received an “ACCEPT” process status response, and that they have been sent to Oracle Accounts Receivable (AR) before the account can be closed and the payment method(s) deleted. This will allow EPS the ability to reprocess any failed aggregate records for the payment method with Global Payment and send the corresponding records to Oracle AR before the account is officially closed.
2019-10-23 | 2019-09-10 | 1535 | eBilling | ETR 1535 - Pending Ach Debit Payment Method with Pending Primary Prioritization not activated when verified and nickname is unable to be updated | Manage Payment Methods | 03-High | Implemented 1/12/2020 | An issue will be corrected in which customers are unable to verify ACH debit payment methods that are pending primary prioritization. Currently, when a customer attempts to verify micro debits or update the nickname for an ACH debit payment method which has a Pending status and is also pending primary prioritization, an error occurs in the system. The error causes the payment method to incorrectly remain in Pending status. If the current verification attempt is not the third and final attempt on the ACH debit payment method, the customer can activate the payment method through another verification attempt after the ACH debit has been made “primary” at 6 PM the same day. However, if the current verification attempt is the final attempt on the ACH debit payment method, manual intervention is needed in order to activate the account.
2019-10-23 | 2019-09-05 | 1528 | eBilling | ETR 1528 - User not able to access Transaction History Report Drill Down unless first transaction in display table is ACH DEBIT | Transactional Reports | 03-High | Implemented 1/12/2020 | An issue will be corrected on the Transaction History Report that prevents users from accessing the report’s drill down unless the first transaction displayed in the Transaction History filtered results table is an ACH Debit Non-Deferred transaction. The report will be updated to enable users to click directly on any transaction within the filtered results table in order to access the drill down for that transaction.
2019-10-23 | 2019-09-04 | 1527 | eBilling | ETR 1527 - Performance Issue with the Daily Account balance Reconcilaition Job | eBilling Admin Reports | 02-Medium | Implemented 1/12/2020 | Performance will be improved for the Daily Account Balance Reconciliation process, which runs overnight. The improved performance will lower the risk of the process running so long that it interrupts daytime transaction processing.
2019-10-23 | 2019-03-11 | 1383 | eBilling | ETR 1383 - Add data validation for NCSC customer number | Manage Products/Services | 01-Low | Implemented 1/12/2020 | EPS will be updated to validate the National Customer Support Center (NCSC) Customer Number entered by the user when they link their address quality services to their EPS account. Currently NCSC Customer Number field does not have any data validation, allowing invalid characters (e.g., spaces, letters) to be entered and accepted. When this happens, the linkage may not save correctly and cannot be delinked without manual intervention.
2019-09-03 | 2019-08-28 | 13514 | PostalOne! | Mail.dat - Update Postage Statement processing to allow both less than or equal to 3.5 ounces and greater than 3.5 ounces (heavy letters) on a single PS | Mail.dat & Mail.XML | 02-Medium | Implemented 1/12/2020 | Mail.dat postage statement processing for USPS Marketing Mail will be updated to allow pieces with both less than or equal to 3.5 ounces and greater than 3.5 ounces (heavy letters) on a single postage statement. Currently, PostalOne! Mail.dat processing fails to total such pieces into a single postage statement line. As a result, Mail.dat error 7079 is generated and the postage statement cannot be completed. As a temporary workaround until the issue is resolved, users can separate USPS Marketing Mail pieces that are less than or equal to 3.5 ounces and letters greater than 3.5 ounces onto separate postage statements.
2019-07-01 | 2019-06-17 | 13358 | PostalOne! | eInduction - BCG Shipping Summary Report Appointment ID Search Returning Error | Mail.dat & Mail.XML | 02-Medium | Implemented3/15/2020 | Mail.dat and Mail.XML processing will be updated to correct an error that is currently generated when Business Customer Gateway (BCG) users attempt to search the Shipping Summary Report by Appointment ID.
2019-05-06 | 2019-05-03 | 13238 | PostalOne! | BCG/BMEU statements line A17 (copies discount) can exceed the total number of copies. | Domestic Postage Processing | 02-Medium | Implemented 1/12/2020 | The PostalOne! System will be updated to add a validation check for Periodicals postage statements to ensure that the number of copies claiming a discount (line A17 - Copies Discount) does not exceed the total number of copies (line A1 - Total Copies). Currently, Periodicals postage statements submitted through the Business Customer Gateway (BCG) or Business Mail Entry Unit (BMEU) have no validation to restrict line A17 from exceeding the total number of copies on line A1, which could potentially enable the net postage to be a negative amount. If a statement is incorrectly finalized with a negative net postage amount, the accounting information cannot be sent to the Enterprise Payment System (EPS).
2019-04-29 | 2019-04-23 | 13188 | PostalOne! | Shipping Summary reports shows error inducting 18 digit container barcode | Postage Statement Wizard | 02-Medium | Implemented 8/23/2020 | The PostalOne! System Postal Wizard will be updated to properly handle Mailer IDs (MIDs) that have only 6 digits when generating the Intelligent Mail container barcode (IMcb) placard for eInduction. Currently, the Postal Wizard logic does properly format 6-digit MIDs when generating the IMcb placard. Consequently, the container is unable to be released for induction because the resulting barcode contains only 18 digits instead of the required 21 digits. The Shipping Summary report shows the error: "The IMcb for the container is not equal to 21 characters. The container was not released for induction to the field." The Postal Wizard IMcb placard generation logic will be updated to pad 6-digit MIDs with zeroes on the front to ensure that the resulting barcode is 21 digits in length.
2019-02-27 | 2018-11-16 | 1240 | eBilling | CR 1240 - Saving more than 91 permit records at a time causes Internal Server Error | Manage Products/Services | 02-Medium | Closed | EPS permit linkage functionality will be updated to allow a larger number of permits to be linked to one EPS account. Currently, a system error is incorrectly generated if a user attempts to link more than 91 permits to an EPS account.
2019-02-11 | 2018-11-29 | 12823 | PostalOne! | ETR - Correct POSASP XSD validation failure | Interface | 02-Medium | Implemented 3/17/2019 | The PostalOne! System SASP XML Schema Definition (XSD) will be updated to accommodate new values (V, X) in the Address Type in support of the most recent Mail.XML version. The current XSD does not support the updated values. As a result, the SASP data load fails validation for files containing the updated values.
2018-12-31 | 2018-10-31 | 12754 | PostalOne! | Dashboard – Unable to View Postage Register for Large Mailings | Domestic Postage Processing | 01-Low | resolved & closed 5/22/2020 | The PostalOne! System Dashboard will be updated to properly display the Postage Statement Register for large mailings. Currently, an error appears when users attempt to access the Postage Statement Register for a large mailing. The message "Page Cannot Be Displayed" or "Error in Pagination" displays.
2018-12-17 | 2018-09-27 | 1189 | eBilling | ETR - Users are able to view permits for crids they do not have access to | Manage Products/Services | 04-Critical | Resolved | EPS will be updated to correct an issue that incorrectly allows users to view permits for Customer Registration IDs (CRIDs) they do not have access to if the permit is actively linked in EPS.
2018-12-17 | 2018-09-25 | 1187 | eBilling | AchAggregate transactions not posting to Global Pay due to performance issues | Process Transactions | 03-High | Resolved | Performance will be improved for the aggregate process that posts Automated Clearing House (ACH) Debit transactions to the Global Pay system to alleviate intermittent failure of the process.
Priority - Updated Values
01-Low = Wish For 02-Med = Could Have 03-High = Should Have 04-Critical = Must Have

## Issues Detected Before JAN 2020
Date Added to List | Detected on Date | Item ID | Application | Summary | Module | Priority | Release Notes | Comments
2019-11-20 | 2019-11-12 | 1583 | eBilling | Performance 1583 - Commercial Mailing andShipping Details report not loading for impacted customer | PostalOne! Reports | 01-Low | The Commercial Mailing and Shipping Details report will be updated to improve performance so that the report can be consistently accessed. Currently, the report fails to load in some circumstances when a large date range is selected.
2019-09-03 | 2019-08-18 | 13496 | PostalOne! | Regression Automation: For Monthly Cancellation Report, system generates a blank page when searching with PI Permit and search with a date on or before 08/01/2019 | Reports | 02-Medium | The Monthly Cancellation Report will be updated to prevent the PostalOne! System from generating a blank page when the user attempts to search with a Permit Imprint (PI) permit using a date on or before 08/01/2019.
2019-07-01 | 2019-06-25 | 13377 | PostalOne! | Piece-Weight Information report on Postage Statement Incorrect | Dashboard | 01-Low | The Piece-Weight Information report accessed through the postage statement will be updated to reflect the correct number of pieces, count of copies and advertising percentage for Periodicals. Currently, when a Periodicals postage statement is accessed through the Dashboard, the Piece-Weight Information report shows an incorrect piece count. The number of copies and advertising percentage are missing from the report. As a temporary workaround until the issue is resolved, users can view this information on the Version Summary Report through the Job Details page.
2019-06-11 | 2019-06-11 | 13349 | PostalOne! | In the Interface between PO! and EPS - Total number of copies on non-periodical postage statements needs to be provided , Permit holder CRID (optional field) also needs to be provided |  | 02-Medium | The interface between the PostalOne! System and the Enterprise Payment System (EPS) will be updated to include the following additional fields: total number of copies for non-periodical postage statements, and permit-holder Customer Registration ID (CRID). These two fields provide details that cannot be retrieved from the existing data sources currently used by the interface.
2019-05-21 | 2019-05-13 | 1444 | eBilling | CR 1444 - Add the NCSC customer account number to NCSC transactions on the Transaction History Report | Transactional Reports | 02-Medium | The Transaction History Report will be updated to include the National Customer Support Center (NCSC) Customer Account Number for NCSC transactions.
2019-05-14 | 2019-05-02 | 13233 | PostalOne! | MSTR new user loading issue | BMA Microstrategy Reports |  | The PostalOne! System process to send data to the MicroStrategy database for new MicroStrategy users will be updated to correct an issue that currently prevents new users from being able to log in to their MicroStrategy accounts. A change to the source of this data was made in a previous release; however, the logic to account for this change was not made in the process that handles new MicroStrategy user data.
2019-05-06 | 2019-05-03 | 13237 | PostalOne! | EPS - CoMail FPP statements causing duplicate Periodical charges | Domestic Postage Processing | 02-Medium | For Co-Mail postage statements in Finalized Pending Payment (FPP) status and using an Enterprise Payment System (EPS) account, the PostalOne! System will be updated to prevent duplicate Periodicals charges from being sent to EPS.
2019-04-29 | 2019-04-18 | 1417 | eBilling | CR 1417: Add Customer Reference ID to Transaction History Report | Transactional Reports | 02-Medium | The Transaction History report will be updated to include a column for the Customer Reference ID.
2019-04-08 | 2019-04-07 | 13155 | PostalOne! | MicroStrategy link on Mail Entry Additional Postage Assessment is incorrect |  |  | The link for MicroStrategy Reports at the top of the PostalOne! System Mail Entry Additional Postage Assessment Report page will be corrected to enable users to access the MicroStrategy reports directly from this page. The current link uses an incorrect Uniform Resource Locator (URL) and results in a blank page when users attempt to access it.
2019-04-08 | 2019-04-07 | 13154 | PostalOne! | Footer -> Other Links -> BCG - Broken Link | Mailer View Functionality |  | The link to access the Business Customer Gateway (BCG) from the footer of the Postal Wizard page will be updated to point to the correct Uniform Resource Locator (URL). Currently, users are not able to access the BCG when clicking the BCG link via the following path from the Postal Wizard page footer: Other Links --> BCG.
2019-03-27 | 2019-03-26 | 13133 | PostalOne! | SN Incidents Related to incorrect Display of CAPs | Interface | 02-Medium | The PostalOne! System Dashboard will be updated to properly display the account type. Currently some accounts are incorrectly displayed as Centralized Account Processing System (CAPS) accounts even though they are not CAPS accounts. As a result, impacted users are unable to determine the correct account type. As a temporary workaround until the issue is resolved, users can log off and log back into a new PostalOne! System session in order to view the correct account status/type.
2019-03-11 | 2019-03-08 | 13083 | PostalOne! | Fee renewal E-mail notice does not display expiration date and is mailed despite fee being renewed | Administrative Module | 02-Medium | Fee renewal notification messages will be updated to show the fee expiration date. Currently, fee renewal notifications state that fees for the permit will be due in 30 days; however, the actual expiration date is not included in the notice. In addition, validation checks will be implemented to prevent mailing a renewal notice if the fee has already been paid.
2019-02-27 | 2019-01-29 | 1341 | eBilling | CR 1341 - ePOBOL PO Box changes EPS accounts after it is opened the refund fails when the Box is closed | Process Transactions | 03-High | The EPS refund process will be updated to account for the scenario where a customer changes the EPS account that is paying for an Enterprise PO Boxes Online (EPOBOL) box. Currently in this scenario, when the customer attempts to close the box, the refund fails. This is because the current refund process associates the refund back to the original transaction (i.e., the original EPS account before the customer changed it). As a result, EPS Customers that change the account that is paying for the box are unable able to receive a refund from closing their linked EPOBOL box. As a temporary workaround until the issue is corrected, EPOBOL can manually close the box, then EPS App Support can manually submit the refund transaction.
2019-02-27 | 2017-03-07 | 385 | eBilling | CR - Add Check Returns Report | Miscellanous eBiling Customer Reports | 02-Medium | A new report will be created showing returned check details for EPS transactions. The new report, "Check Returns Report" will be available to EPS external customers for their transactions, and to EPS Administrative users. | CR dropped
2019-02-27 | 2017-02-06 | 351 | eBilling | CR - EPOBOL Detailed Report - Remove original purchases from report if purchase was returned and cancelled | Miscellanous eBiling Customer Reports | 02-Medium | Original purchases will be excluded from the EPOBOL Detailed Report in cases where the original purchase was returned to EPOBOL and the box was cancelled. | CR covered elsewhere
2019-02-25 | 2019-01-24 | 12976 | PostalOne! | Dashboard is not displaying the Periodical Postage in the Postage $ column on the Job Information Summary for comail mailings | Dashboard | 01-Low | The PostalOne! System Dashboard will be updated to consistently display the Periodicals Postage in the "Postage $" column on the Job Information Summary page. Currently, when users click a Job ID on the Dashboard Job Information Summary page, the total postage is not displayed for co-mail and master Periodicals eDoc statements.
2019-02-25 | 2019-01-23 | 12975 | PostalOne! | BCG out of town permit fee payment for master fee not able to be paid | Interface |  | The Business Customer Gateway (BCG) Fee Payment logic will be updated to properly handle fee payments for out-of-town Business Reply Mail (BRM) permits with no associated parent (master) BRM permit (i.e., an "orphan" BRM permit). Currently, the BCG Fee Payment logic is not handling these correctly, with the result that the relevant fees cannot be paid. The affected fees are the BRM permit fee (master account) and the BRM annual maintenance fee (sub-account).
2019-02-25 | 2018-10-04 | 12673 | PostalOne! | Mailing Agent is a required field for 3541 Combined Periodicals in New Postal Wizard Setup | Postage Statement Wizard | 02-Medium | For Periodicals and Combined Periodicals (PS Form 3541 or PS Form 3541 Combined), the Postal Wizard will be updated to not require entry of a Mailing Agent for mail owners who submit the form for themselves (i.e., without a mail agent). Mail agents will retain the ability to submit Periodicals and Combined Periodicals on behalf of their clients through the Postal Wizard. However, entry of a Mailing Agent on the form will not be required for mail owners who submit the form for themselves. Currently, when mail owners submit PS Form 3541 or PS 541 Combined for themselves through the Postal Wizard, the system incorrectly requires entry of a Mailing Agent. | researching
2019-02-11 | 2019-02-01 | 13000 | PostalOne! | On the Fee Expiration Dates Report under Balances and Fees, the Fee Due Date and the Paid column are sometimes incorrectly showing the fee as due and unpaid. | Administrative Module | 02-Medium | The PostalOne! System Fee Expiration Dates Report accessed from the Balance and Fees page will be updated to accurately reflect the Fee Due Date and Paid column. Currently, the report sometimes incorrectly shows a paid fee as due and unpaid. As a temporary workaround until the issue is resolved, users can view accurate fee details on the Customer Information page.
2019-02-11 | 2018-11-01 | 12759 | PostalOne! | Mailer Fee Calendar does not display EPS account numbers | Mailer View Functionality | 02-Medium | The Mailer Fee Calendar will be updated to include the Enterprise Payment System (EPS) account number for permits linked to an EPS account. The Mailer Fee Calendar is accessed from the Balance and Fees page and displays a list of permits along with their associated account numbers. | researching
2019-02-11 | 2018-10-12 | 12695 | PostalOne! | Mail.dat - Rounding for Metered Correct Statements resulting in .01 Postage Due | Mail.dat & Mail.XML | 01-Low | Mail.dat postage statement processing will be updated to correct a rounding issue for Metered Correct postage statements that can incorrectly result in $0.01 postage due for Metered Correct mailings submitted by Mail.dat. Currently, Mail.dat rounds the USPS Total Adjusted Postage to two decimal places, but the Afffixed Postage remains rounded to 3 decimal places. | researching
2019-01-16 | 2018-08-29 | 12618 | PostalOne! | The mail.dat client failed to upload job due to exceed the allowable size limit of pdr file | Mail.dat & Mail.XML | 02-Medium | The Mail.dat client fails to upload jobs that exceed the allowable size limit for Piece Detail Record (PDR) files. The current size limit for PDR files is 2,147,483,647 bytes. As a temporary workaround, users can split the PDR file or use a Piece Barcode (PBC) file instead. | researching
2019-01-16 | 2018-08-28 | 12614 | PostalOne! | Inc 3495594 - CAPS Transaction History Report missing Adjustment Transactions | Interface | 02-Medium | The CAPS Transaction History Report will be updated to correct a defect in data retrieval that prevents the report from displaying Adjustment Transactions. | researching
2019-01-07 | 2019-01-04 | 12909 | PostalOne! | PO! not sending piece rate and pound rate to EPS for Commercial ePacket (3700P) | BMEU | 01-Low | For Commercial ePacket statements using an Enterprise Payment System (EPS) permit, the piece rate and pound rate will be displayed in the EPS Line Details Report at the account level. Currently, EPS is not receiving this information from the PostalOne! System for Commercial ePacket transactions using an EPS permit.
2018-12-31 | 2018-11-29 | 12825 | PostalOne! | Mail.dat Firm Bundles with One or More ComboPacks | Mail.dat & Mail.XML | 02-Medium | The PostalOne! System Mail.dat application will be updated to allow Periodicals mailings to have Firm Bundles that contain Polybags/ComboPacks. This change will allow for piece charges to be calculated correctly to one piece per Firm Bundle as compared to one piece per ComboPack. This update adds Firm Bundles to ComboPacks; it does not change the logic of ComboPacks in other Non-Firm Bundles (an existing feature). To accommodate this change, Mail.dat validation error 4825 will be modified as outlined below. FROM: 4825 - When the .pqt Combo-Pack ID is populated for .mpu Mail Piece Unit - Class of 2 = Periodicals or 5 = Per Pending, the .pqt Number of Pieces must be greater than or equal to 1 on the CQT Database ID (s) which have the highest .cpt Component - Periodical Ad Percentage and .cpt Component - Rate Type of R = Regular and .pqt Number of Pieces must be equal to 0 on the other CQT Database ID(s) within each unique .pqt Combo-Pack ID + .pqt Package ID + .csm Container ID. TO: 4825 (Non-Firm) - When the .pqt Combo-Pack ID is populated for .mpu Mail Piece Unit - Class of 2 = Periodicals or 5 = Per Pending and the .pqt Package Level is not Firm Bundle, the .pqt Number of Pieces must be greater than or equal to 1 on the CQT Database ID (s) which have the highest .cpt Component - Periodical Ad Percentage and .cpt Component - Rate Type of R = Regular and .pqt Number of Pieces must be equal to 0 on the other CQT Database ID(s) within each unique .pqt Combo-Pack ID + .pqt Package ID + .csm Container ID. 4825B (Firm) - When the .pqt Combo-Pack ID is populated for .mpu Mail Piece Unit - Class of 2 = Periodicals or 5 = Per Pending and the .pqt Package Level = A Firm Bundle , the .pqt Number of Pieces must be equal to 1 on the CQT Database ID (s) which have the highest .cpt Component - Periodical Ad Percentage and .cpt Component - Rate Type of R = Regular and .pqt Number of Pieces must be equal to 0 on the other CQT Database ID(s) within each unique + .pqt Package ID + .csm Container ID. | researching
2018-12-31 | 2018-10-31 | 12754 | PostalOne! | Dashboard – Unable to View Postage Register for Large Mailings | Domestic Postage Processing | 01-Low | The PostalOne! System Dashboard will be updated to properly display the Postage Statement Register for large mailings. Currently, an error appears when users attempt to access the Postage Statement Register for a large mailing. The message "Page Cannot Be Displayed" or "Error in Pagination" displays. | resolved & closed on 5/22/2020; moved to closed items tab
2018-08-29 | 2018-08-01 | 12573 | PostalOne! | PostalOne Mail Owner Report and Customer Mail Report Total Postage do not match | Reports | 01-Low | For Mail.dat submissions, PostalOne! System Report processing will be updated to correct a display issue. The total postage reflected for a customer on the Mail Owner Report does not match the postage for the customer in the Customer Mail Report. | researching
2018-08-22 | 2018-07-03 | 12513 | PostalOne! | Incorrect Mailing Volume Information on Mail Owner/Preparer Scorecard | Reports | 02-Medium | The Mailer Scorecard will be updated to consistently reflect accurate mailing volume information. Currently, a defect in summarization of the mailing data from the PostalOne! System is resulting in incorrect volume counts for some mailers on the Mailer Scorecard. The impacted volume counts are reported on the Mailer Scorecard as lower than the actual volume. | researching